## Top Claims Projects
CountyCare Claims and Configuration Project Updates Updated 3/20/2021
# | Type | Project | Impacted Providers | Description | Updates / Resolution | Status
66 | PROCESSING ERROR | Program Code "09" QMB Codes incorrectly processed as covered benefit Remark Code: n/a | ALL Providers | Per HFS Practitioner Fee Schedule, codes identified as Program Code "09" are only covered benefits for qualified Medicare beneficiaries, or QMBs. CountyCare has incorrectly been processing claims for these codes/services as covered. Updates will be made to the claims processing system to ensure these codes are no longer covered and appropriately denied. | System configuration completed 1/16/20 Claims identification completed. Claim recoveries underway - letter sent mid April. All recoveries paused due to Public Health Emergency (PHE) Recovery hold lifted - claim impact analysis complete Recoveries in progress December 2020-March 2021 | In Progress
109 | PROCESSING ERROR | Anesthesia P5 Underpayments Remark Code: n/a | Anesthesia Providers | Value for P5 is calculating at 2 instead of 4 | System configuration complete Claims reprocessing complete | Complete
124 | PROCESSING ERROR | Specialist claims for anesthesia underpaid | Anesthesia Providers | A multiple procedure reduction applying incorrectly to surgical procedure codes based upon surgical indicators "I" and "M" | System configuration complete Claims reprocessing complete | Complete
129 | RATE UPDATE | IL HFS Medicaid Reimbursement Fee Schedule (Rate Change): Practitioner Fee Schedule, Effective 10/01/2020 | ALL Providers | On 11/23/2020, HFS released the Practitioner Fee Schedule effective 10/1/2020 | System configuration complete Impacted claim review in progress | In progress
130 | RATE UPDATE | CMS Approval Letter Homemaker Rate Increase - delayed to 04/01/2021 | Waiver/Atypical Providers | On 11/23/2020, HFS provided the CMS letter approving 2021 Homemaker rate increase. A notice of effective date delay was shared by HFS on 12/17/2020 | System configuration complete | Complete
133 | PROCESSING ERROR | BH Eval codes pricing outside of EAPG | Hospitals | BH Evaluation codes performed in the ER are pricing per DASA fee schedule and not EAPG | System configuration complete Impacted claim review in progress | In progress
135 | RATE UPDATE | Follow Up to Homemaker Rate Increase for 01/01/2021 (Enhanced rate for providers w insurance) | Waiver/Atypical Providers | On 12/15/2020, HFS provided homemaker rate updates effective 1/1/2021 | System configuration complete Impacted claim review in progress | In progress
140 | RATE UPDATE | FINAL Rate Year 2021 MPA & MHVA Rates to MCOs' | Hospitals | On 1/11/2021 HFS released Final RY2021 MPA MHVA Rates (after Appeal) effective 10/01/2020 | System configuration complete Claims reprocessing complete | Complete
141 | RATE UPDATE | Provider Notice - Coverage for Applied Behavioral Analysis (ABA) Services for Children 0 through 20 Years Prior Approval | ALL Providers | On 1/22/2021, HFS announced additional program and billing guidelines for Applied Behavior Analysis (ABA) services and coverage guidelines effective November 1, 2020 | System configuration complete Claims reprocessing complete | Complete
142 | RATE UPDATE | IL HFS Practitioner Fee Schedule - Updated 01/22/2021 | ALL Providers | On 1/28/2021, HFS provided a Practitioner Fee Schedule update effective date retro back to 12/31/2020 | System configuration underway | In progress
143 | RATE UPDATE | HFS Fee Schedule: COVID Vaccination Update 1/27/21 | ALL Providers | On 1/31/2021, HFS provided an update to COVID-19 vaccine rates | System configuration complete Claims reprocessing complete | Complete
144 | RATE UPDATE | Applied Behavioral Analysis (ABA) Fee-for-Service Fee Schedule | Retro 11/1/2020 | On 2/3/2021, HFS released for Applied Behavior Analysis (ABA) fee schedule effective November 1, 2020 | System configuration complete Claims reprocessing complete | Complete
145 | RATE UPDATE | COVID Fee schedule update effective 3/1/2021 | ALL Providers | On 2/23/2021, HFS released an updated COVID fee schedule to reduce reimbursement of U0003 & U0004 and add pricing to eligible providers for U0005 effective 3/1/2021 | System configuration underway | In progress
146 | RATE UPDATE | Updated Podiatry Fee Schedule | Podiatry Providers | On 2/23/2021, HFS released an updated podiatry fee schedule with retroactive effective date of 1/1/2021 | System configuration underway | In progress
147 | RATE UPDATE | Revised APR-DRG & EAPG Calculators w/ Revised U of I Rate Information - Effective 01/01/2021 | ALL Providers | On 3/1/2021, HFS released revised APR-DRG & EAPG Calculators with retroactive effective date of 1/1/2021 | System configuration underway | In progress
148 | RATE UPDATE | Retroactive Rate Changes for LTC Facilities | LTC Providers | On 3/1/2021, HFS released retroactive rate changes for five LTC facilities | System configuration underway | In progress
149 | RATE UPDATE | Retroactive Rate Update LTC & SLF Rates for 01/01/2021 | LTC, SMHRF, SLF Providers | On 3/5/2021, HFS released rate changes for LTC, SMHRF, and SLF Providers with retroactive effective date of 1/1/2021 | System configuration underway | In progress
150 | RATE UPDATE | DASA Rate Sheet - Revised February 2021 | SUPR/DASA Providers | On 3/9/2021, HFS released an updated SUPR/DASA rate sheet as of February 2021 | System configuration underway | In progress
151 | RATE UPDATE | Telehealth Update : Hospitals Billing as the Telehealth Originating Site | Hospitals | On 3/9/2021, HFS released an updated Telehealth billing guidance for hospitals as originating site. Revenue Code 0780 & HCPCS Code Q3014 are now required on claims with 3/1/2021 received date and after | System configuration underway | In progress

## ARCHIVED
CountyCare Claims and Configuration Project Updates HISTORICAL 03/20/21
# | Type | Project | Impacted Providers | Description | Updates / Resolution | Status
|  | H0004 Denials for CMHCs Remark Code SNES | CMHC Providers Only | For some CMHCs (not all), due to a pricing build error, code H0004 was incorrectly denying between claim processed dates of 8/2/2016 through 03/15/2017 (not date of service, but date or processing). | Error has been corrected. Impacted claims will be reprocessed; timely filing will not apply. | Completed. Claims recalc completed 3/27/17. Claims payment expected on 3/21 and 3/28 check runs.
|  | CMHC Incorrect Denials for "duplicate" claim Remark Codes for duplicates: 18, IDUP | CMHC Providers Only | Prior to January 2017, CMHC claims where all information (member, provider, procedure, units, etc) was the same were being denied without reviee of Place of Service (POS) or Modifier. | Upon receiving updated directive from HFS in late January 2017, updated poolicies and system to review POS and Modifiers on CMHC claims to determine true duplicate ot not. Impacted claims will be reprocessed; timely filing will not apply. | Completed. Claims recalc completed on 3/6/17. Claim payment on either 3/2/17 check, or 3/16/17 check.
|  | Hospice Rev Code 0658 Claim Denials Remark Code SNES | Hospice Providers Only | Hospice providers were receiving denials for Rev Code 0658. | CountyCare policy was updated to accruately process Hospice claims for Rev Code 0658 per HFS guidelines. Impacted claims will be reprocessed; timely filing will not apply. | Completed. Claims recalc completed 3/8/17. Claim payment on either 3/16/17 check, or 3/21/17 check.
|  | H0002 Pre 7/1/16 Dates of Service Unit Limitation | DASA Providers only | For claims prior to DOS 7/1/16, there was a 4 unit limitation imposed. Reviewing policy to potentially enhance or remove limitation. | CountyCare updated policy to remove a unit limitation for this code. | Completed. Claims recalc completed 3/3/17. Claim payment on either 3/2/17 check, or 3/16/17 check.
|  | EAPG Edits - Underpayments on Claims No Remark Code | Institutional Providers | Received reports of claims underpaying- ER, Obs, Outpatient. Currently researching and reviewing provided examples. | Claims defaulting to "lesser of" logic (submitted charges vs. allowable charges) at the clain line level. System is being corrected to remove this limitation. Impacted claims will be reprocessed; timely filing will not apply. | Completed. System Updates complete 4/7/17. Claims recalc completed 5/1/17. Claims payment expected on 5/2 and 5/9 check runs.
|  | Ungroupable DRG Denials (may also say Invalid Dx) Remark Codes A8, IDID | Institutional Providers | Institutional claims being denied with Remark Code A8 for "ungroupable denials"or IDID for "diagnosis code is invalid" starting with DOS during/after October 2016. This is ONLY for inpatient- not for LTC. Refer to the IUPD, IPD4, and IPD2 project for invalid Dx denials for LTC. | Necessary system updates for APR-DRG and/or ICD-10 completed in systems as of 4/12/2017. | Completed. System Updates complete 4/12/17. Claims recalc completed 4/26/17. Claims payment expected on 5/2 check run.
|  | EAPG Edits - Modifier 25 Remark Code 3145 | Institutional Providers | Received reports of claim lines denying incorrectly to use/non-use of modifier 25. Remark Code - 3145 on EOPs. Researching and reviewing provided examples. | Claim with improper use of Modifer 25 will no longer be denied- but will pay at correct rate (Modifier 25 enhanced rate will not apply). | Completed. System Updates complete 4/7/17. Claims recalc completed 4/27/17. Claims payment expected on 4/20, 4/25, and 5/2 check runs.
|  | Invalid Dx Claim Denials Remark Codes IUPD, IPD4, IDP2 | Long Term Care (SMRF, ICF, SNF, NH) Providers | LTC Providers receiving denials for LTC claims when specific Dx codes are present (I10, ZXXX, etc). | CountyCare reviewed HFS guidance and current system set up, will be removing this edit denial for LTC (SMRF, ICF, SNF, NH) taxonomies. Impacted claims will be reprocessed; timely filing will not apply. | Completed. Claims recalc completed 4/7/17. Claims payment expected on 3/28 and April check runs.
|  | Incorrect Denials of ER Revenue Codes and HCPCS Combinations Remark Code: IERB | Institutional Providers | Claims submitted with ER revenue codes and correct HCPCS code combinations incorrectly denied | System updated 10/29/17. Claims will no longer deny for correct ER revenue codes and HCPCS combinations. | Completed 1/1/2018 Claims payment TBD; dependent on funding from HFS.
|  | EAPG Denials for Incorrect Bundling/Billing of Codes - NCCI Edits Remark Codes 2220, 2240 | Institutional Providers | Received reports of claim lines denying incorrectly for these Remark Codes. | After futher review, this remark code denied appropriately and either pulled on codes that won't pay even with a NCCI approved modifier or on codes that will pay with a NCCI approved modifier, but was not billed with a NCCI approved modifier.
|  | ER/Observation Claims with no Payment Remark Code: MX, ONMC | Institutional Providers | Received reports of ER/Observation claims going out with no payment. | The issue is being investigated to determine why claims aren't pricing. Once the issue is resolved, a recalc will be performed on the affected claims. | In Progress Claims recalc ETA 1/26/18 Claims payment TBD; dependent on funding from HFS.
|  | Denials for DRG values/PPS Codes Billed on Outpatient Claims Remark Code: DRGO | Institutional Providers | Claims submitted with DRG/PPS Codes denying incorrectly on Outpatient claims | System updated 10/29/17. Claims will no longer deny DRG/PPS Codes billed on Outpatient claims. | Completed 2/6/2018. Claims payment TBD; dependent on funding from HFS.
|  | Non-Hospital Providers denying for Principal Dx Codes Remark Codes: X18 and X19 | Institutional (non-hospital) Providers | Received reports of non-hospital institutional claims denying incorrectly for principal diagnosis codes. | System updates in progress for non-hospital institutional claims to remove denial logic. Once system is updated, claims will be resubmitted. | Completed 2/20/18. Claims payment TBD; dependent on funding from HFS.
|  | Non-Hospital Providers denying for POA Indicators Remark Codes: X29 and X30 | Institutional (non-hospital) Providers | Received reports of non-hospital institutional claims denying incorrectly for no POA indicator billed. | System updates completed 2/8/18. Recalc is completed as of 4/2/18. | Completed 4/2/18. Claims payment TBD.
|  | Non-Covered Services Denials Remark Code: X998 | DASA and Waiver Providers | Received reports of DASA and waiver claims denying for procedure not covered by HFS. | System updates completed 2/21/18. Recalc is completed as of 3/30/18. | Completed 3/30/18. Claims payment TBD.
|  | Denials for APL codes Remark Code: XA24 | Institutional Providers | Claims denying for not being billed with APL codes, which was incorrect. | System updates completed December 2017; claims currently being adjudicated. | Completed 04/09/18.
|  | EAPG Edits - Modifiers 59, XE, XU, etc Remark Codes 3143, 3170, 3178 | Institutional Providers | Claim lines denying incorrectly due to use/non-use of modifier 59. | Claims analysis complete; claims currently being resubmitted. | Completed 5/25/18.
|  | Denials for Drug Unit Qualifier Remark Code: X508 | Institutional and Non-institutional Providers | Claim lines denying incorrectly due to ME drug unit qualifier billed. | Claims analysis complete; claims currently being resubmitted. | Completed 6/1/18.
|  | Professional Claims denying for APL when APL does not apply. Remark Code: A39 | Professional Providers | Some claims submitted on HCFA1500/837P were incorrectly denying in error for the A39 edit related to APL. | System updates completed early June, claims reprocessing completed 6/21/18. | Completed 6/21/18.
|  | Transportation Billing Guideline Updates - New Modifiers Allowed Remark Code: NAMB | Transportation Providers | Emergency transportation provider claims denied with remark code NAMB due to incorrect modifier billed. HFS recently provided clarification that Medicaid MCOs should also allow modifiers S, X, E, and N in addition to other already acceptable modifiers. | Process updated to allow updated modifiers; claims reprocessing complete. | Completed 7/3/18.
|  | Invalid Emergency Transportation Denials - License Plate Character Issues within Claim Text Note Remark Code: NAMB | Transportation Providers submitting two spaces at end of license plate number | Emergency transportation provider claims denied with remark code NAMB due to invalid formatting of license plate. Submitting two spaces (to submit full eight characters required in field) however denying for only showing seven due to claims processing system error. | Process updated to no longer deny; claims reprocessing complete. | Completed 7/10/18.
|  | Homemaker Services- Enhanced Rates Remark Code: n/a | Waiver Providers | HFS released updated rates (regular and enhanced) for homemaker services retro to DOS 8/1/17 | System updates completed June 2018. Impacted claims identified and reprocessed. | Completed 7/14/18.
|  | Waiver EO Denials Remark Code: EO | Waiver Providers | Waiver claims incorrectly denying for coordination of benefits (requiring EOP from primary).. | Claims retraining completed. Full system pull of all waiver possible claims denied for EO completed. | Completed 7/27/18.
|  | Hospice LTC Claims with R&B - Other lines Zero Paying Remark Code: n/a | Hospice Providers | Manually pricing the R&B (at 95% of per diem) was cuasing all other claims lines to zero out. | Manual workaround defined and in place. System review concurrent for automated solution in review. Impacted claims reprocessed. | Completed 7/28/18.
|  | Observation Claims Pricing at $0 Remark Code: n/a | Institutional Providers | Observation lines pricing at $0 with claim status of Paid. | System review is currently underway; once confirmed if error, system will be updated and claims will be sent for mass resubmittal. | Completed 7/31/18.
|  | APL/HCPCS Code Required on Claim Remark Code: A39 Related to XA24 | Institutional Providers - Psychiatric Type A and B Services | Claim lines denying incorrectly when psychiatric type A and B services are billed correctly. | System updates completed 7/26/18. Additional concerns raised with system build- further review necessary and underway. Claims reprocessing underway. | Completed 10/23/18.
|  | ER, Obs and Psych UB Claims Denying for XA24 Remark Code: XA24 related to A39 | Institutional Providers | ER, Obs and Psych UB Claims Incorrectly Denying in some instances with XA24 - "CLAIM CONTAINS HCPCS NOT ON THE AMBULATORY PROCEDURE LISTING (APL) THAT MUST BILLED FEE FOR SERVICE" | System updates completed late September. Claims reprocessing underway. | Completed 11/7/18.
|  | Claims Incorrectly denied for P03 Remark Code: P03 | All Providers; majority Waiver, DASA (IMD), CMHC. | Revised process for P03 (Not Eligible Provider per HFS) hold and review; reconciling incorrect holds currently in existence on provider records in system. | Provider record reconciliation completed 8/26/18. Claims impact analysis and full recalc underway. | Completed 11/7/18.
|  | LTC Quarterly Rate Updates Released for 10/1/18 Remark Code: n/a | LTC Providers | Quarterly rates released by HFS for LTC Providers. | Currently in review for system updates. | Completed 10/15/18.
|  | X799 - Surgical Indicator "I" Denials Remark Code: X799 | Multiple Providers | Per HFS Fee schedule “I = Incidental/minor procedure. Procedure may or may not pay separately when billed with a visit or other surgical codes”. Claims were incorrectly denying. | System updates completed 9/28/18 | Completed 11/1/18.
|  | RATE UPDATE - Hospital Add Ons FY 2019 Hospital DSH, MHVA, MPA, Safety Net Add On Rates Effective 10/1/18 | Hospitals | HFS released updated Hospital 2019 FY (10/1/18 - 9/30/19) add on rates (HFS released on 9/28/18). | Rates updated 10/17/18. | Completed 10/17/18.
|  | RATE UPDATE - Hospice Hospice Rate Updates Effective 10/1/18 | Hospice Providers | HFS released updated Annual Hospice Rate Changes effective 10/1/18 (released 9/24/18) | Rates updated 10/26/18. | Completed 10/26/18.
|  | RATE UPDATE - CMHC CMHC Fee Schedule Updates Effective 11/1/18 | CMHC Providers | HFS released updated CMHC Fee schedule for 11/1/18. | Rates updated 11/8/18. | Completed 11/8/18.
|  | RATE UPDATE - Podiatry Podiatry Fee Schedule Updates Effective 10/1/18 | CMHC Providers | HFS released updated Podiatry Fee schedule effective 10/1/18 (HFS released on 10/25/18). | Rates updated 11/2/18. | Completed 11/2/18.
|  | SLF Denials for Rev Code Requires HCPCS code Remark Code: X322 | SLF Providers | Claims denying for "EAPG- REVENUE CODE IS REQUIRES HCPCS CODE ON SAME LINE." | System Review underway. | Completed 11/6/18.
|  | XB93 - FQHC Claims - Denied for Billing Taxonomy Invalid for POS Billed Remark Code: XB93 | FQHC Providers | FQHC claims billed FFS for visits in inpatient setting denying incorrectly. | System updates completed mid November. Claims reprocessing during November. | Completed 11/21/18.
|  | SLF Denials for Invalid Admitting Diagnosis Remark Code: X18 | SLF Providers | Received reports of SLF claims denying incorrectly for principal diagnosis codes. | System updates under review and update. System update complete 11/19/18. Claims Recalc ETA 11/27/18. | Completed 11/21/18.
|  | New CPT/HCPCS Codes Effective 1/1/2018 Remark Code: X998 | Radiology/Diagnostic Imaging Providers Anesthesthia Providers | New Radiology and Anesthesia CPT/HCPCS codes were added to the 2018 HFS fee schedules. Claims were inappropriately denied for Services Not Covered. | System updates completed. Claims review and reprocessing underway. Originally completed 8/23/18. REOPENED: Several providers were mistakenly excluded from the initial reprocessing. | Completed 11/29/18.
|  | Incorrect Claim Denials for Incorrect, Invalid, and Missing Diagnosis Remark Code: DIAG | All Providers | Claims denying for "DIAG" - invalid/missing Dx code - for new 10-1-18 ICD-10 Dx codes. | System corrected 11/20/18. | Completed 11/30/18.
|  | HFS Updated Hospital Contracted Rates 7/1/18 Remark Code: n/a | Hospitals | HFS released updated Hospital Rate Sheets in early July. | System updates completed 8/24/18. Claims analyzed and resubmitted 11/8, and 11/12. Doing second sweep to catch missing hospital (St. Bernard, Mercy, etc) | Completed 11/30/18.
|  | COB Automated Denials for Waiver, LTC Remark Code: EO | Waiver, LTC | Manual processes and system updated for waiver/EO (pend claims for review vs deny). Some waiver/EO claims still denying for EO. | Determined automatic system script for claims finalization incorrectly auto-finalizing denials. Corrected existing processes and reprocessed claims in August. Subsequent claim denied for auto script. | Completed 11/29/18. All impacted claims reprocessed 12/28/18.
|  | Incorrect Denials for Missing Admission Dx for Procedure Remark Code: X27 | SLF Providers | SLF provider claims incorrectly denying for missing Dx procedure code. Impact < 25 claims total. | System configuration ETA 12/3. System configuration complete 12/5. Claims recalc complete 12/11. | Completed 12/11/18.
|  | Incorrect denials when billing non-APL codes on CMS1500/837P Remark Code: HCFA | Hospitals | Hospitals claims incorrectly denying when billing non-APL codesCMS1500/837P. Roughly two hospitals impacted, ~3000 claims. | System updates completed 11/30/18. Claims recalc completed 12/18/18. | Completed 12/18/18.
|  | RATE UPDATE - DME DME Fee Schedule + Key Updates Effective Date: 12/1/18 | DME Providers | HFS Released updated fee schedule key to providers/MCOs 12/12/18 | Review and any necessary updates in progress | Completed 1/9/19.
|  | FQHC IUD Denials Remark Code: EC or X456 | FQHCs | Claims for IUD accurately billed FFS (not billed with Encounter) were inaccurately denying. | System configuration confirmed accurate. Claims resubmission for historical denials underway. | Completed 2/5/19
|  | COB Automated Denials for Waiver, LTC Remark Code: EO | Waiver, LTC | About 1100 claims remained/denied between December and January 2018/2019. Manual processes and system updated for waiver/EO (pend claims for review vs deny). Some waiver/EO claims still denying for EO. | Updated all aspects of system and have reprocessed all impact claims. | Completed 2/6/19
|  | XA85 - Paying E&M codes on Encounter clinic claims Remark Code: XA85 | Isolated FQHCs (<6) | For some isolated encounter clinic claims, found paying on E&M codes in addition to the T1015 codes. Need to correct system flaw allowing this payment and recoup the funds. | System configuration completed 12/28/18. Recovery/recoupment of overpayments underway - letters being sent by 2/15. | Completed.
|  | RATE UPDATE - Practitioner Fee Schedule Practitioner Fee Schedule Updates Effective Date: 1/1/19 | All Practitioners | HFS Released 1/1/2019 rates to providers/MCOs 1/15/19. | Rate updates completed 1/25/19. | Completed 1/25/19
|  | FQHC POS 21 – Claim paid $0 Remark Code: MX | FQHCs | FFS claims for place of service (POS) 21 from FQHC providers were triggering "MX" paid remark code and inaccurately paying at $0. | System configuration confirmed accurate. Claims resubmission for historical denials underway. | Completed 2/7/19.
|  | CMHC MUE Edit Denials for H2000; H2016 with billed units > 1 Remark Code: X448 | CMHC Providers | X448 edit denial for "MUE (Medicaid MEdically Unlikely Edits) total units billed exceeds the allowed units" is firing incorrectly for CMHCs billing H2000 & H2016 when billing with unit amounts > 1. | System updates in progress to remove these codes from that edit. Manual recalc to pay 1 unit completed 1/7/19. System fix completed to pay multiple unites 1/11/19. Claims recalc to pay all units 95% complete. | Completed 2/11/19.
|  | Denials for OTHER DIAGNOSIS OR ICD-10 PROCEDURE CODE IS INVALID OR DISABLED Remark Code: X3 | Inpatient/Institutional providers | Inpatient/Institutional claims denying for X3 beginning in mid/late November, spike in early December. | Confirmed edit as currently firing is inaccurate. Approx 200 claims finalized between 10/1/18 - 12/18/18 denied incorrectly. Claims reprocessing underway. | Completed 2/13/19.
|  | Incorrect Denials for Interim Claim Must Be billed at least 30 days Remark Code: XB40 | Hospitals | Denial incorrectly firing on Type of Bill (TOB) XX1, XX2, XX4, and XX7. Should only fire on XX3 TOB. Impact < 70 claims total. | System configuration updates completed 2/5/19. Claims Reprocessing Underway | Completed 2/21/19.
|  | RATE UPDATE - Podiatry Podiatrist Fee Schedule Effective Date: 1/1/19 | Podiatry Providers | HFS Released updated fee schedule to providers/MCOs 2/14/19 | Deployed in production 3/1/19. | Completed 3/1/19
|  | H2000 Requiring PA Incorrectly Remark Code: S2 or OS2 | CMHC Providers | H2000 was defined to require PA starting 2/1/19. Upon further review, the PA configuration was in error and if being removed. The code will NOT require PA. | System updated in progress. Claims will be reprocessed once complete (approx. ~1300) | Completed 3/8/19
|  | Increasing Prior Auth Threshold for DME from $>500 to >$1000 Remark Code: N/A | DME Providers | Updating existing prior authorization policy so only DME services that pay > $1000 require prior auth. Will be in effect for DOS 3/1/19 and after. | updates Completed. Review for any denials between 3/1 and 3/18 underway. | Completed 3/8/19
|  | Hand Priced Policy Updates Remark Code: N/A | DME, Orthotics, Prosthetics Providers | CountyCare updating existing Hand-Priced codes policy to align with HFS guidance. | In Progress for 3/1/19 effective date. Reference notice online under Provider Notices for more details. Any claims for DOS 3/1 - 3/14 under review for potential reprocessing needed. | Completed 3/15/19
1 | PROCESSING ERROR | Incorrect Denials for Mobile Crisis Response Services (submitted prior to November 2018) - Procedure Code S9484 Remark Code: X998 | CMHC Providers | Mobile Crisis Response S9484 – finalizing approximately 400 claims that denied prior to November 2018 for this code. | System updates completed Nov 2018. | Completed 3/25/19
3 | PROCESSING ERROR | DASA Denials for Invalid Place of Service Remark Code: XE00 | DASA Providers | DASA claims incorrectly lfagging edit denial XEOO: "DASA SERVICE IS ONLY ALLOWED IN PLACE OF SERVICE 03, 21, 22, 55, 57, OR 99." - when POS is accurate. This is not ALL DASA- mainly DASA providers where NPPES is not updated with correct primary taxonomy of DASA approved taxonomy. | Under Review. ~500 claims rejected; will be reprocessed once system configuration updates completed. ~2600 pending system configuration updates (have not denied). Denied Claims Completed 3/4/19. Pending Claims flush completed 3/25/19 | Completed 3/25/19
6 | PROCESSING ERROR | DME Quantity Limit/Frequency Denials Remark Code: several | DME Providers | Claims denying for quantity limits for DME services, e.g. "DME SERVICE EXCEEDS QUANTITY LIMITS. SVC LIMITED TO 15 PER 30 DAYS." Per billing, not exceeding the limitation. | System research indicates due to system daily count methodology, Day 1 is counted as Day 0, which cuts full count allowance short one day. System updates re-review underway. Claims recalc analysis wil begin once system re-review completed. | Completed 4/1/19
4 | PROCESSING ERROR | Institutional Denials for Invalid Admit Date for Interim Claim Remark Code: XC40 | LTC / SLF /DASA / IP Providers | Received reports of LTC/SLF claims denying incorrectly forinvalid admit date for interim claims. E.G. Claims for TOB XX3 and XX4 submitted where Admit Date is = Service From date. | System configuration corrected 10/17/18. LTC/SLF Claims completed 1/4/19. DASA/IP Claims ETA 1/31/19. Updated TOB XC40 logic to define what providers the rule should apply to. | Completed 4/2/19
3 | PROCESSING ERROR | Observation Claims Pricing at $0 Remark Code: n/a | Institutional Providers | Observation lines pricing at $0 with claim status of Paid. | System updates completed. Claims Reprocessing underway. | Completed 4/19/19
4 | PROCESSING ERROR | DASA 7/1/18 Rate Updates - Review Payment Amounts Remark Code: n/a | DASA Providers | New DASA rates effective 7/1/18 - received input from a few providers some claims not paying updated rates. | Under Review. | Completed 4/30/19
8 | RATE UPDATE | RETRO RATE UPDATE - DASA Effective Date: 2/1/19 | DASA Providers | HFS Released 2/1/19 rates to providers/MCOs on 4/3/19 | In Progress | Completed 5/15/19
9 | RATE UPDATE | RETRO RATE UPDATE - DME DME 2019 Rate Updates Effective Date: 1/1/19 | DME Providers | HFS Released 1/1/19 rates to providers/MCOs on 4/3/19 | In Progress | Completed 5/15/19
| PROCESSING ERROR | OB-GYN - Maternal/Child Add-Ons Remark Code: n/a | OBGYN Providers | Maternal/child add on rate not paying for OB providers. | System configuration updates completed 9/18. | Completed 5/17/19
| RATE UPDATE | RATE UPDATE - FQHC FQHC 2019 Rates Effective Date: 1/1/19 | FQHC Providers | HFS Released 2019 rates to providers/MCOs 12/20/18. | Rate updates completed 1/17/19. QA and review of claims submitted prior to 1/17/19 underway. | Completed 5/23/19
2 | RATE UPDATE | RATE UPDATE - Practitioner Fee Schedule (Second HFS Release) Practitioner Fee Schedule Updates Effective Date: 1/1/19 | All Practitioners | On 3/8/19 - HFS Released updates to the 1/1/2019 rates originally released on 1/15/19. These NEW HFS updates include ~164 codes with updated rates; effective back to 1/1/19. | Completed 5/31/19 | Completed 5/31/19
11 | PROCESSING ERROR | FQHC POS 21 – Authorization denials related to maternity and newborn visits Remark Code: S2 | FQHC Providers | FFS claims for place of service (POS) 21 for services related to maternity and newborn visits from FQHC providers inaccurately denying for prior authorization. Inpatient and Professional services related to standard maternity IP stays (48 hours for vaginal delivery and 96 for caesarean) do not require PA. | System configuration completed on 5/15/19. | Completed 6/14/19
7 | PROCESSING ERROR | Modifier 26 Denials - Professional Component Remark Code: X303 | Professional Providers | Investigating denials for ~20 procedure codes where Modifier 26 does not include rate on the HFS Practitioner Fee Schedule ands claim does not include professional/technical component. Per reports, HFS allows payment. | Completed 6/17/19 | Completed 6/17/19
| RATE UPDATE | 1115 Waiver Claims Remark code: n/a | Waiver Providers | Need pricing and OBRA files from HFS for claims related to 1115 Waiver program | System updates completed on 5/3/19. | Completed 6/19/19
10 | PROCESSING ERROR | Historical Anesthesia Denials Remark Codes: S2, OS2 | Anesthesia providers | CountyCare removed PA requirement for anes, codes would like review of PA denials and retroc recalc back to 1/1/17 DOS (confirm) | Under review. 1. Confirm DOS for look back 2. Need to pull all denials for OS2 and S2 for anesthesia | Completed 7/17/19
6 | RATE UPDATE | RATE UPDATE - LTC LTC 4/1/19 Quarterly Rate Updates Effective Date: 4/1/19 | LTC / SLF Providers | HFS Released 4/1/2019 rates to providers/MCOs 3/22/19. | Completed 7/19/19 | Completed 7/19/19
29 | RATE UPDATE | RATE UPDATE - DASA v23 Effective Date: n/a | DASA Providers | HFS Released updates to the rate sheet for DASA providers in August. | System Configuration Completed 9/3/19 | Complete
30 | RATE UPDATE | RATE UPDATE - HOSPICE Effective Date: 9/1/19 | HOSPICE Providers | HFS Bulletin 7/3/19 regarding new Service Line Date and Occurrence Code 55 requirements for hospice. These billing changes are effective with dates of service on or after September 1, 2019 (previously August 1, 2019). | System configuration completed 8/23/19 | Complete
24 | PROCESSING ERROR | Interim Bills for Hospital Outpatient TOB 13X Remark Code: XC40 | Behavioral Health Hospitals | PHP/IOP Claims denying inaccurately for XC40: INVALID ADMIT DATE FOR INTERIM CLAIM when billed with TOB 13X. | System configuration bug identified, in process for re-configuration. Once configuration completed, impacted claims will be identified and reprocessed. System configuration completed 8/26. Claims completed 8/31/19. | Complete
25 | PROCESSING ERROR | MLTSS Overypayments for Non-Covered Services Remark Code: n/a | ALL Providers | Inaccurate configuration for covered services under the MLTSS program allowed several thousand claims to pay vs. deny for non-covered services. | System configuration in QA/testing. System comfiguration completed 8/23/19. System configuration completed 8/23/19. Claims that were pending the system fix completed 8/30/19. Claims Recoupments to begin early October. | Complete
29 | PROCESSING ERROR | Prior Auth Denial for Service with Initial No-PA Requirements Remark Codes: S2, OS2 | CMHC, Home Health, PT/OT/ST providers | Services with initial benefit limits that do not require PA (e.g. first 6 visits do not require PA) - claims for services within initial period are denying for no PA | System configuration completed on 5/15/19. Claims ETA in phases. CMHC , Home Health completed. Therapy next. | CMHC, Home Health claims completed 8/12/19. ETA 9/9/19 - delay for PT/OT/ST. New ETA 9/20/19
30 | PROCESSING ERROR | P03 Denials for Enrolled Providers Remark Code: P03 | All Providers | System error resulted in several providers receiving denials that state they are not enrolled to provide Medicaid Services. | Impacted provider records fixed 8/15/19. Recalc report will be ran to determine impact after configuration is in place Claim reprocessing complete 8/30/19 | Complete
31 | PROCESSING ERROR | Out of Network Denials for In Network Providers Remark Code: OS2 | All Providers | Out of Network Auth denials are incorrectly flagging on claims for some PAR providers. | System configuration fix completed 8/12/19 Claims reprocessing complete 8/31/19 | Complete
31 | PROCESSING ERROR | Claim Lines Paying at $0 Incorrectly Remark Code: MX* | DASA, CMHC | Claims incorrectly processed to pay $0 on lines that should have paid for the codes outlined below, with counts. H2015 – 127 claims H2016 – 3,674 claims H0005 – 705 claims T1016 – 28 claims | System configuration completed. Claims reprocessed. | Complete
32 | PROCESSING ERROR | Hospice Rev Code 0658 Claim Denials for MLTSS Members Remark Code MLTS | Hospice Providers Only | Hospice R&B codes for MLTSS members are denying incorrectly. | Issue identified and in process of fix. System fix in place ETA 9/20/19 Claims reprocessing ETA 9/27/29 | In Progress ETA 9/27/2019
33 | PROCESSING ERROR | Additional Review of Claim Denials for MLTSS members Remark code: MLTS | ALL Providers (submitting claims for MLTSS members) | Have received several inquiries regarding these denials, reviewing several examples: *SMRFH Claims *Home Modification (S5165) | Confirmed the below situations were icorrectly denying: *SMRFH Claims *Home Modification (S5165) System configuration completed. Claims reprocessing. | System Updates Completed. Claims in reprocessing ETA 9/27/19
34 | PROCESSING ERROR | MLTSS COB Denial Remark Code Incorrectly Appended to Claims Remark Code: EO | ALL Providers (submitting claims for MLTSS members) | During processing of all MLTSS claims pending, approx 70 claims flagged the incorrect "EO" denial code. | Issue identified, all claims have been reprocessed to remove the invalid "EO" denial code. Claims either denied for other valid reasons, or reprocessed to pay. | In Progress ETA 9/27/19
36 | PROCESSING ERROR | Waiver Claims Denying for No Authorization Remark Code: S2 | Waiver Providers | Waiver claims denying for no prior authorization incorrectly | Claims Reprocessing completed; adjudicator error. Re-education completed. | Complete
38 | PROCESSING ERROR | APC Rate Code Denials for Outpatient EAPG Claims Remark Code: X905 | Institutional Providers | Outpatient claims processed between 8/26 and 9/12 were pricing against APC rates instead of EAPG rates. Most claims did not go out on check run and will be reprocessed before going out on EOP (but may see this remark in the portal). | System corrected 9/12/19 Claims analysis underway. | In Progress ETA 10/4/19 for claims
39 | PROCESSING ERROR | LTC Auth denials after FHN/Aetna transitions Remark Code: n/a | Long Term Care Providers | After transition of Family Health Network members to CountyCare on 11/1/17, prior FHN members currently under LTC care should not have been denied due to no auth for the first three months After transition of Aetna members to CountyCare on 1/1/18, prior AETNA members currently under LTC care should not have been denied due to no auth for the first three months | Denied claim impact analysis underway to ensure capture denials where members was previously FHN/Aetna. In review, most claims have already been reprocessed and paid. Only 12 claims remained that needed reprocessing. Reprocessing Compete- Claims Pending Check Run. | Complete
40 | PROCESSING ERROR | LTC Auth Denials after 6/1/19 Remark Code: n/a | Long Term Care Providers | AS of 6/1/19 DOS, LTC/Custodial Care services no longer require prior authorization. Claims for DOS after 6/1/19 have been denied for no PA. | Re-training for claim adjudicators completed. Denied claim impact completed. Claims Reprocessing completed 9/11/19. | Complete
43 | RATE UPDATE | RATE UPDATE - LTC Retro Rates Effective Date: 7/1/2019 | LTC and SMHRF Providers | HFS Released updates to the rate sheet for LTC and SMHRF providers in September. | Configuration confirmed already in system 8/15/19. | Complete
44 | RATE UPDATE | RATE UPDATE - Waiver Effective Date: 7/1/2019 | Waiver Providers | HFS Released updates to the rate sheet for waiver providers in September. | System Configuration deployed 10/2/19. Claims reprocessing underway, impact TBD. | In Progress
45 | RATE UPDATE | RATE UPDATE - MPA and MHVA Effective Date: 10/01/2019 | Institutional Providers | HFS Released updates to MPA and MHVA rates for institiutional providers in September. | System Configuration deployed 10/9/19. Claims reprocessing underway, impact estimated <10 total claims. | In Progress
45 | RATE UPDATE | RATE UPDATE - Podiatry Fee Schedule Effective Date: 9/11/2019 | Professional Providers | HFS Released updates to the podiatry fee schedule in September. | System Configuration in progress- reviewing codes overlapping on Pracitioner Fee schedule to ensure accurate payments. Awaiting feedback, ETA within next few weeks. | In Progress
46 | RATE UPDATE | RATE UPDATE - Practitioner Fee Schedule Effective Date: 9/11/2019 | Professional Providers | HFS Released updates to the practitioner fee schedule in September. | System Configuration deployed 10/2/19. Claims reprocessing underway, impact TBD. | In Progress
12 | PROCESSING ERROR | VFC- Vaccinations for Children IX/XI -HISTORICAL RECONCILIATION Remark Code: n/a | Primary Care Providers | Appropriate payment and configuration regarding reimbursement for VFC program (specific 834 segment data + provider billing requirements) | FQHC configuration and claims corrected. Practitioner configuration underway; interim solution for manual claims reprocessing in progress. Claims Reconciled through 4/12/19. Will run additional claims between 4/12/19-8/31/19 to ensure all claims are reprocessed and paid appropriately. Claims impact and reprocessing for DOS 4/12/19-8/30/19 within next 3-4 weeks following 10/16/19. | In Progress
15 | PROCESSING ERROR | Transportation Claims Paying at Incorrect Rates Remark Code: n/a | Transportation Providers | System configuration needs to be updated to pay providers at the correct rates according to where they are located, not the pickup zip code location | System configuration fix in process - ETA 9/15/19 - delayed to 9/23/19 Claims are underpaid and overpaid. Recalc/recoup report will be ran to determine impact after configuration is in place. ETA 10/17/19 for impact analysis. Claims reprocessing to begin ASAP once have claims. | In Progress
16 | PROCESSING ERROR | Procedure Code S5130 Underpaying Remark Code: n/a | Waiver Providers | For a few isolated providers, claims paying at incorrect prior rate of $4.29 for procedure code S5130 | System updates in progress to stop underpayments. Claims reprocessing will occur once system corrected. Several providers complete; finalizing configuration for all. | In Progress. ETA Late October/Early November.
17 | PROCESSING ERROR | Maternal/Child Add-Ons Remark Code: n/a | Primary Care Providers; Pediatricians, OBGYN providers | 1) MCH value can be anything, not just Y 2) Providers added to IMPACT file to receive add ons - need to add providers to system so claims can pay add ons | System configuration updates in progress based on updated listing received from HFS on 5/31/19. Please note the reprocessing of claims will include recoupments for providers who were not accurately displayed on IMPACT Provider but received PCP add-ons since 1/1/2018. System Configuration was complete 9/24/19. Impact Analysis completed 10/11/19. Claims underpayments reprocessing underway. Claims overpayment reprocessing to occur in November. | In Progress ETA 10/30/19 for all underpayments
20 | PROCESSING ERROR | Therapy Claims Denying for MUE Limits Remark Code: X448 | Therapy Providers | Therapy codes denying for exceeding total allowable units (MUE limitations) - HFS therapy fee schedule has a different unit amount thus the denials are incorrect. | System configuration needed to correct edit - ETA 8/31/19 9/16: Several codes corrected; isolating these codes for immediate reprocessing while remaining codes fixed. Claims reprocessing will occur once edit is corrected. | In Progress ETA Delayed to Mid-October for full fix
23 | PROCESSING ERROR | Value Code 80/81 Remark Code: X910 | Institutional Providers | Reports received of claims issues around Value Codes 80/81 - inaccurate denials. | Value Code 80 triggering incorrect X910 denial edit. Agree there are incorrect denials, researching root cause for analysis and remedication. Once configuration completed, impacted claims will be identified and reprocessed. System configuration fix completed 9/24/19 Claims Reprocessing Complete. | Complete
41 | PROCESSING ERROR | LTC Claims “Short-Paid” due to PA Short of Days of Stay Remark Code: UEX | Long Term Care Providers | Reports from LTC providers PAs only for 180 days vs true count for 6 months, hence short paying claims by a few days for last month of PA. | Claims Reprocessing complete 10/11/19. | Complete
48 | RATE UPDATE | RATE UPDATE - DASA v25 Effective Date: 7/1/19 | DASA Providers | HFS Released updates to the rate sheet for DASA providers in August. | System Configuration underway | In Progress ETA 11/11/19
49 | PROGRAM UPDATE | ORP Delayed to 1/1/20; Soft Launch for Informational Edits 11/1/19 | ALL Providers | Federal program requiring ordering/ referring/ prescribing practitioners to be enrolled in the Illinois Medical Assistance Program. | Effective with dates of service on and after January 1, 2020 the Department will reject claims if the required ORP information is missing or invalid, or if the ORP is not enrolled with the Department. Beginning November 1, 2019, CountyCare will append informational remark codes to claims where the required ORP claim information is missing or invalid, or if the ORP is not enrolled with the Department. | In Progress
50 | PROCESSING ERROR | MLTSS HOSPICE R&B Rev Code 0658 Denials Remark Code: MLTS (not specific to this, general MLTSS denial) | Hospice Providers | HOSPICE R&B Rev Code 0658 claims, when billed with Procedure Code, are denying for non-covered in error. Rev 0658 billed alone is not flagging denial edit. | System configuration fix ETA 10/18/19 Claims Reprocessing begin Week of 10/21/19 | In Progress
38 | PROCESSING ERROR | APC Rate Code Denials for Outpatient EAPG Claims Remark Code: X905 | Institutional Providers | Outpatient claims processed between 8/26 and 9/12 were pricing against APC rates instead of EAPG rates. Most claims did not go out on check run and will be reprocessed before going out on EOP (but may see this remark in the portal). | System corrected 9/12/19 Claims reprocessing completed. | Complete
37 | RATE UPDATE | RATE UPDATE - DASA v24 Effective Date: 7/1/19 | DASA Providers | HFS Released updates to all codes for DASA providers in August. | System configuration completed 9/17/19. Claims reprocessing complete. | Complete
42 | RATE UPDATE | RATE UPDATE - Supportive Living Program Effective Date: 7/1/2019 | SLP Providers | HFS Released updates to the rate sheet for SLP providers at the end of August. | System Configuration completed 9/19. Claims reprocessing complete. | Complete
45 | RATE UPDATE | RATE UPDATE - MPA and MHVA Effective Date: 10/01/2019 | Institutional Providers | HFS Released updates to MPA and MHVA rates for institiutional providers in September. | System Configuration deployed 10/9/19. Claims reprocessing underway, impact estimated <10 total claims. System Configuration Complete. Claims Reprocessing Complete. | Complete
46 | RATE UPDATE | RATE UPDATE - Practitioner Fee Schedule Effective Date: 9/11/2019 | Professional Providers | HFS Released updates to the practitioner fee schedule in September. | System Configuration deployed 10/2/19. Claims reprocessing complete. | Complete
47 | RATE UPDATE | RATE UPDATE - Hospice Rates + Value Code 61 Effective Date: 10/1/19 | Hospice Providers | On 9/27/19 HFS released updated Hospice Rates (annual changes) effective 10/1/19 | System Configuration deployed 10/29/19. Claims reprocessing complete. | Complete
15 | PROCESSING ERROR | Transportation Claims Paying at Incorrect Rates Remark Code: n/a | Transportation Providers | System configuration needs to be updated to pay providers at the correct rates according to where they are located, not the pickup zip code location | System configuration completed 9/24/19. Claims are underpaid and overpaid. Claims Impact Analysis complete. Claims reprocessed and paid Week of 11/4/19. | Complete
25 | PROCESSING ERROR | MLTSS Overpayments for Non-Covered Services Remark Code: n/a | ALL Providers | Inaccurate configuration for covered services under the MLTSS program allowed several thousand claims to pay vs. deny for non-covered services. | System configuration in QA/testing. System comfiguration completed 8/23/19. Pending Claims processing began 8/26. System configuration completed 8/23/19. Claims reprocessing completed 8/30/19. Overpayment Reprocessing completed; recoveries completed by 11/27. | Complete
45 | RATE UPDATE | RATE UPDATE - Podiatry Fee Schedule Effective Date: 9/11/2019 | Professional Providers | HFS Released updates to the podiatry fee schedule in September. | System Configuration completed. Claims reprocessing underway - ETA 12/15/19 (very small impact) | Complete
48 | RATE UPDATE | RATE UPDATE - DASA v25 Effective Date: 7/1/19 | DASA Providers | HFS Released updates to the rate sheet for DASA providers in August. | System Configuration completed Claims reprocessing complete. | Complete
50 | PROCESSING ERROR | MLTSS HOSPICE R&B Rev Code 0658 Denials when billed with Procedure Code Remark Code: MLTS (not specific to this, general MLTSS denial) | Hospice Providers | HOSPICE R&B Rev Code 0658 claims, when billed with Procedure Code, are denying for non-covered in error. | System configuration fix ETA 11/15/19 Claims Reprocessing completed 11/26/19. | Complete
55 | PROCESSING ERROR | FQHC IUD Denials Remark Code: XB86 | FQHCs | Claims for IUD accurately billed FFS (not billed with Encounter) are inaccurately denying. | System configuration completed 12/13/19. Impacted claims reprocessed and paid 12/31/19. | Complete
56 | RATE UPDATE | RATE UPDATE - CMHC Effective Date: 7/1/19 | CMHCs | HFS released updates to rate sheet for CMHC providers in October | System configuration fix: 11/13/19 Claims reprocessing completed. | Complete
58 | PROCESSING ERROR | Hospital IUD Denials Remark Code: multiple | Hospital Providers | Claims for IUD are inaccurately denying. | Under review. System fix 12/6/19. Claims reprocessed 12.27 Claim payments 12/31. | Complete
60 | RATE UPDATE | RATE UPDATE - FQHC rates for Calendar Year 2020 Effective Date: 1/1/2020 | FQHCs | HFS Released CY 2020 FQHC Encounter Rates on 11/20/2019. | System configuration completed 12/20/19. | Completed
5 | RATE UPDATE | RATE UPDATE - Outpatient Rates Outpatient Rate Schedule Updates Effective Date: 7/1/18 (Critical Access hospitals); 3/8/19 (Non-Critical Access Hospitals) | Institutional Providers | On 3/15/19 - HFS Released updates to the outpatient rates for all hospitals. Critical Access hospital rates are retro-effective 7/1/18. Non-Critical Access hospital rates are retro-effective 3/8/19. | Issues 5, 18, 21, 35 part of comprehensive claims analysis and reprocessing effort. System configuration completed 4/11/19. Additional system configuration specific to isolated provders identified and configured 8/9/19. Identifying impacted claims for reprocessing - received listing of impacted providers 8/26/19. Reprocessing completed; 98% of payments and recoveries to be completed by 11/27/19. Fallout 2% worked and completed by 1/13/20. | Complete
16 | PROCESSING ERROR | Procedure Code S5130 Underpaying Remark Code: n/a | Waiver Providers | For a few isolated providers, claims paying at incorrect prior rate of $4.29 for procedure code S5130 | System updates in progress to stop underpayments. Claims reprocessing will occur once system corrected. Confirmed all providers updated. Claims full reprocessing completed 1/10/20. | Complete
18 | RATE UPDATE / PROCESSING ERROR | Outpatient/EAPG Base Rates Incorrect Remark Code: n/a | Institutional Providers | EAPG base rates for some providers continued to pay at 2017 rates throughout 2018. Need to reconcile base rates and reprocess claims. | Issues 5, 18, 21, 35 part of comprehensive claims analysis and reprocessing effort. System configuration fix completed 8/23/19. Claims are underpaid and overpaid. Recalc/recoup report will be ran to determine impact after configuration is in place. Reprocessing completed; 98% of payments and recoveries to be completed by 11/27/19. Fallout 2% worked and completed by 1/13/20. | Complete
21 | RATE UPDATE / PROCESSING ERROR | OB/Newborn Policy Adjustor Effective 7/1/2018 Remark Code: n/a | Institutional Providers | OB/Newborn Policy Adjustor effective 7/1/18 to adjust weights from 1.35 to 1.54 depending on severity of illness was not implemented | Issues 5, 18, 21, 35 part of comprehensive claims analysis and reprocessing effort. System configuration completed 7/5/19. Claims are underpaid and will be reprocessed when impact report is received. Reprocessing completed; 98% of payments and recoveries to be completed by 11/27/19. Fallout 2% worked and completed by 1/13/20. | Complete
35 | RATE UPDATE / PROCESSING ERROR | Safety Net Add-On Incorrectly Paying on Psych/Rehab Claims Remark Code: n/a | Safety Net Hospitals | Per HFS, safety net add on to only pay per acute med day. Configuration was set to pay on acute, psych, and rehab. Claims will be reprocessed to recoup extra monies | Issues 5, 18, 21, 35 part of comprehensive claims analysis and reprocessing effort. Claims will be reprocessed as part of broader reprocssing project for incorrect EAPG/OP and DRG/IP rates. Reprocessing completed; 98% of payments and recoveries to be completed by 11/27/19. Fallout 2% worked and completed by 1/13/20. | Complete
44 | RATE UPDATE | RATE UPDATE - Waiver Effective Date: 7/1/2019 | Waiver Providers | HFS Released updates to the rate sheet for waiver providers in September. | System Configuration deployed 10/2/19. Claims reprocessing underway, impact TBD. Confirmed all providers updated. Claims full reprocessing completed 1/10/20. | Complete
59 | PROCESSING ERROR | Per Diem Inpatient Claims Overpaying for Non-Covered Days Remark Code: n/a | Institutional Providers | Inpatient hospital claims for per diem providers incorrectly paying on days not covered under authorization. Impacting claims processed or re-processed between 9/20/19 - 11/4/19. Mainly impacting BH/MH institutional providers. | System configuration fixed 11/4/19. Claims Identification completed 12/9/19. Claims reprocessing completed 12/27/19. | Complete
62 | RATE UPDATE | RATE UPDATE - DASA v26 Effective Date: 8/12/19 | DASA Providers | In December, HFS Released retro rate updates for specific DASA providers | System configuration completed 12/14/19. No claims impacted. | Complete
65 | PROCESSING ERROR | Incorrect Denials around Member Eligiblity Remark Code: ME | ALL Providers | From 1/1/20 - 1/10/20, certain claims with DOS on or after 1/1/20 were flagging an incorrect "Member Not Eligible" edit and denying with remark code ME. Approximately 1300 claims incorrectly denied. | Impacted providers were notified between 1/13 - 1/15. System configuration completed 1/16/20. Claims identification completed. Claims reprocessing completed 1/17/20. | Complete
22 | RATE UPDATE | VFC- Vaccinations for Children XIX/XXI - 9/1/19 HFS Program Updates Effective Date: 9/1/19 | Primary Care Providers | HFS released notice 8/12/19 stating will require providers to use vaccine acquired through the VFC Program for all children enrolled in HFS’ medical programs, including Title XXI and state-only funded children ages 0 through 18. Providers will no longer be reimbursed for the cost of privately purchased vaccines for CHIP and state-only funded children if the vaccine is available through the VFC program. There is no change in coverage policy for Title XIX (Medicaid Program) children. | Program update requirements currently under review to determine necessary system reconfigurations. Configuration completed 12/20/19. Claims impact and reprocessing for DOS 9/1/19 and after 1/31/20 (for 85%+ claims; ETA 2/21/20 for 100% of claims completion). All reprocessing completed 2/7/20. | Complete
51 | PROCESSING ERROR | VFC Claims not paying $6.40 when billed with E&M Code Remark Code: XB68 | Professional Providers | Beginning mid-October 2019, when billing VFC on same claim as E&M, total amount due to be paid is incorrectly paying out due amount less $6.40. | System reconfiguration underway. Pending all claims that meet this criteria so they do not pay out at incorrectly. Configuration complete 12/20/19. Claims reprocessing complete 1/27/20 | Complete
52 | PROCESSING ERROR | H0002 Pricing at $0 Remark Code: n/a | DASA Providers | Claim lines for H0002 are pricing at $0 when submitted with additional claim lines. | System reconfiguration complete. <30 impacted claims to date manually reprocessed as of 12/15/20. All claims completed Feb 16 2020. | Complete
63 | RATE UPDATE | RATE UPDATE - DASA v27 Effective Date: 7/1/19; 10/1/19 | DASA Providers | In December, HFS Released retro rate updates for specific DASA providers | System configuration completed 1/14/20. No claims impact. Complete. | Complete
68 | RATE UPDATE | RATE UPDATE - LTC, SMHRF, Supportive Living Rates Effective Date: 1/1/20 | LTC, SMHRF, SLF Providers | In January, HFS Released additional retro rate updates to these specific provider fee schedules | System configuration completed 2/3/2020. No claims impacted. | Complete
73 | PROCESSING ERROR | ORP Denials Remark Code: RORP; OA-206 | ALL Providers | IMPACT file being used for reference was not sourcing the most recent version. Potential impact: ~50 claims total (minimal impact) | System configuration complete. Claims reprocessing complete 2/27/20. | Complete
57 | RATE UPDATE | RATE UPDATE - Mobile Crisis Response Effective Date: 7/1/19, and retro 8/1/18-6/30/19 | Mobile Crisis Response Providers | In September, HFS released updates to rate sheet for Mobile Crisis Response providers. | System configuration completed 12/18/20. Claims identification complete; claims reprocessing underway. ETA 3/6/20. Timely Filing denials will be waived for corrected claims submutted through 5/15/2020. | Complete
61 | PROCESSING ERROR | Provider Claims Denying for Non-Par- Authorization Required Possible Remark Codes: S2, OS2; M62, CO-197 | ALL Providers | Contracted/PAR provider claims are denying incorrectly for denial code "OS2 - PREAUTHORIZATION REQUIRED FOR OUT OF NETWORK SERVICES." | System configuration fixes for impacted provider records underway. >50% of claims completed. ETA for all 4/1/20. COMPLETED 4/1/20. | Complete
64 | RATE UPDATE | RATE UPDATE - Practitioner Fee Schedule Effective Date: 10/1/2019 | Professional Providers | In December, HFS Released retro rate updates to the 10/1/19 practitioner fee schedule | System configuration completed 12/27/19. Claims reprocessing complete Late March. | Complete
67 | RATE UPDATE | RATE UPDATE - Rate Updates for IP, OP Calculators for CCHHS Effective Date: 1/1/20 | CCHHS only | In late December, HFS Released calculator rate updates effective 1/1/20. | System configuration completed 1/31/2020. Claims impact analysis complete. Recoveries complete | Complete
69 | RATE UPDATE | RATE UPDATE - Final CY2019 Practitioner Fee Schedule Effective: 10/1/19 | Professional Providers | In January, HFS Released final retro rate updates to the 10/1/19 practitioner fee schedule. Specific updates around codes 51798 and J9301; plus clarification on the Psych Add On rates. | System configuration complete 2/5/20. Claims impact analysis complete. Claims reprocessing complete mid April. | Complete
70 | RATE UPDATE | RATE UPDATE - Therapy Fee Schedule Updates Effective Date: 1/1/20 | Therapy Providers | In January, HFS Released retro rate updates for specific Therapy providers | System configuration complete 2/10/20. Claims reprocessing complete. | Complete
71 | RATE UPDATE | RATE UPDATE - DASA v28 Rates Effective: 7/1/19 | DASA Providers | In January, HFS Released retro rate updates for specific DASA providers | System configuration complete 2/7/20. Claims impact analysis complete. Claims reprocessing complete mid March. | Complete
75 | PROCESSING ERROR | Burn DRG 7/1/2018 Rate Update Remark Code: n/a | Hospitals | Burn APR-DRGs 7/1/18 Trauma Services policy adjustor rate update | System configuration complete 3/31/20 Claims impact complete 4/15/20 | Complete
77 | RATE UPDATE | RATE UPDATE - HCBS Rate Updates Effective Date: 4/1/20 | HCBS Providers | On 3/18/20, HFS Released rate updates for HCBS services, effective 4/1/20. | System configuration underway Claims impact analysis complete. Claims reprocessing complete mid April. | Complete
86 | PROCESSING ERROR | Incorrect/missing value code for dialysis/renal provider claims Remark Code: XI07 | Dialysis and Renal Providers | Value code 80 is required when reporting an ESRD revenue code. Claims were incorrectly paying prior, when this value was missing. Fixing system configuration to align with HFS requirements and recovering claims paid in error. | New claims edit has been implemented. Value code 80 is required when reporting an ESRD revenue code. Additionally value code 80 (Covered days) units must match total units billed under revenue code 0821. | Complete
87 | PROCESSING ERROR | Incorrect/missing provider taxonomy submissons for DASA/SUPR MAT claims Remark Codes: XI94, XI95 | DASA Providers Methadone (MAT) | Medication Assisted Treatment (MAT) services must be billed with taxonomy 261QM2800X. Claims were incorrectly paying prior- fixing system configuration to align with HFS requirements and recovering claims paid in error. | New claims edit has been implemented. Methadone clinics must bill with taxonomy 261QM2800X for MAT services, and also cannot bill services other than Medication Assisted Treatment (MAT) H0020 with that taxonomy. | Complete
20 | PROCESSING ERROR | Therapy Claims Denying for MUE Limits Remark Code: X448 | Therapy Providers | Therapy codes denying for MUE limitations - HFS therapy fee schedule has a different unit amount | System configuration needed to correct edit - ETA 8/31/19 9/16: Several codes corrected; isolating these codes for immediate reprocessing while remaining codes fixed. System configuration completed 9/25/19 - still questions around denials- back under review. | Complete
53 | PROCESSING ERROR | Specific Covered Codes Denying Incorrectly for Not of Fee Schedule Remark Code: XA04 | Professional Providers | Certain covered codes are incorrectly denying for "CLAIM LINE IS NOT BILLED IN ACCORDANCE WITH HFS GUIDELINES. REBILL THE CLAIM WITH AN APPROPRIATE BILLABLE CPT/HCPCS FOR THE PROVIDER OR CORRECT THE BILLING/RENDERING PROVIDER" | System Configuration completed 12/2/19. Claims Reprocessing underway, delayed. Claim reprocessing complete June 2020. | Complete
78 | RATE UPDATE | RATE UPDATE - Practitioner Fee Schedule + Fee Schedule Key Retro 1/1/20 Updates Effective Date: 1/1/20 | ALL Providers | On 4/2/20, HFS Released retro rate updates (effective 1/1/20 DOS abd after) to the practitioner fee schedule. Several updates include: addition and removal of 2020 new/obsolete codes, revisions to existing codes, new programs (telehealth, gender affirmation). Revisions were made to the Fee Schedule Key as well. | System configuration complete 5/2/20. Claims reprocessing completed 6/27/20. | Complete
80 | PROCESSING ERROR | Additional Review of Claim Denials for MLTSS and Waiver members Remark code: MLTS; WNC | ALL Providers (submitting claims for MLTSS members) Waiver Providers | Have received several inquiries regarding these denials, disconnect potentially in member eligibility. CountyCare shows member as MLTSS or Non-Waiver, provider believes not MLTSS or that member IS waiver at time of service. Eligiblity mapping under review. | System configuration under review - ongoing through June (reprocessing). | Complete
83 | RATE UPDATE | COVID UPDATES - Fee schedule update for COVID-19 testing (codes U0001, U0002, U0003, U0004 and 87365) | All Providers | Beginning at the COVID-19 pandemic, HFS released COVID-19 testing codes and rates | System configuration complete Claims reprocessing completed 8/11/20. | Complete
84 | RATE UPDATE | COVID UPDATES - Fee schedule update for COVID-19 telehealth billing | All Providers | Beginning at the COVID-19 pandemic, HFS released COVID-19 telehealth billing guidance, codes, and rates | System configuration complete. Claims reprocessing ETA 6/8/2020. Claims payment Wk of 6/8/2020. | Complete
90 | RATE UPDATE | HFS RATE UPDATE: LCP LCSW FEE SCHEDULE EFF 01.01.2020 | ALL Providers | On 6/8/20, HFS released retro LCP/LCSW fee schedule (effective with DOS 1/1/20 and after). This update includes the addition of CPT codes 96130 and 96131 | System configuration completed 7/1 Claims impact analysis complete 7/22/2020 | Complete
92 | RATE UPDATE | Rate Update: SUPR | SUPR/DASA Providers | On 6/19/2020 HFS released SUPR/DASA retro rate updates. | System configuration complete Claims impact analysis complete 8/7/20 | Complete
97 | RATE UPDATE | COVID UPDATES Condition Code DR | ALL Providers | On 5/22/2020, HFS released directive for Condition Code DR to be utilized for COVID-19 related care based on diagnosis occurring for service dates beginning January 27, 2020 and after | System configuration not needed. Complete. | Complete
98 | RATE UPDATE | COVID UPDATES ADS Services | HCBS Providers | On 6/8/2020, HFS released COVID billing directive for HCBS waiver services for ADS with or without CR modifier for DOS 3/16/2020 and after | System configuration not needed. Complete. | Complete
101 | RATE UPDATE | COVID: BH Provider 20% Increase for DOS 3/9 - 6/30 | BH Providers | HFS released guidance early June for 20% rate increases for specific CMHC & DASA/SUPR services | System configuration completed 6/29 Claims Reprocessed completed 7/7 Claims Payment complete 7/14 | Complete
102 | PROGRAM UPDATE | ORP Reinstatement 8/1/20 Remark code: RORP | ALL Providers | Federal program requiring ordering/ referring/ prescribing practitioners to be enrolled in the Illinois Medical Assistance Program. | Effective for claims recieved on and after August 1, 2020 the Department will reject claims if the required ORP information is missing or invalid, or if the ORP is not enrolled with the Department. Beginning August 1, 2020, CountyCare wil also deny claims where ORP claim information is missing or invalid, or if the ORP is not enrolled with the Department. | Complete
12 | PROCESSING ERROR | VFC- Vaccinations for Children IX/XI -HISTORICAL RECONCILIATION Remark Code: n/a | Primary Care Providers | Appropriate payment and configuration regarding reimbursement for VFC program (specific 834 segment data + provider billing requirements) | System fix in place. Configuration completed 12/20/19. Reprocessing historical claims back to 4/12/19 ETA 1/31/20 for >85% of claims. 100% completed by 2/21/20. Underpayment reprocessing completed 2/7/20. | Underpayments complete.
17 | PROCESSING ERROR | Maternal/Child Add-Ons Remark Code: n/a | Primary Care Providers; Pediatricians, OBGYN providers; ALL specialists | 1) MCH value can be anything, not just Y 2) Providers added to IMPACT file to receive add ons - need to add providers to system so claims can pay add ons | System configuration updates in progress based on updated listing received from HFS on 5/31/19. Please note the reprocessing of claims will include recoupments for providers who were not accurately displayed on IMPACT Provider but received PCP add-ons since 1/1/2018. System Configuration was complete 9/24/19. Impact Analysis completed 10/11/19. Initial Provider Underpayments reprocessed 10/4/19; paid 10/9/19. All Provider Underpayments completed and paid Week of 11/4/19. Overpayment reprocessing temporarily held to review further guidance. | Underpayments complete.
103 | RATE UPDATE | HFS Rate Update: SUPR | SUPR/DASA Providers | On 7/20/2020, HFS released SUPR/DASA retro rate updates. | System configuration completed. Claims reprocessing complete. | Complete.
74 | PROCESSING ERROR | Surgical Indicator "I" Claims Remark Code: X799 | Multiple Providers | Claims with surgical indicator "I" per HFS Fee Schedule were incorrectly paying when billed with services with surgical indicator "M". These services should deny and will be recovered. HFS clarification received: Applicable to any provider/COS allowed to bill surgical procedure codes for office POS - not truly overpayments - reprocessing claims that denied for short span. | System configuration complete. Claims reprocessing completed 9/18/20. | Complete
76 | PROCESSING ERROR | Preauth Required for DME Greater than $1,000 Remark Code: DMEK | DME Providers | Claims incorrectly denying for No Prior Auth based on total charges greater than $1,000. | System review and re-configuration underway. 7/30/20 - system configuration complete. Claims Reprocessing complete early September. | Complete
81 | RATE UPDATE | RATE UPDATE - 2019 ACR Rates (UIC and SIU) Effective Date: 1/1/2019 | UIC SIU | On 4/9/20, HFS Released retro rate updates effective for DOS 1/1/2019 and after for UIC and SIU. | System configuration complete 5/7/20 Impacted claims analysis and reconciliation underway; discussions direct with impacted provider (UIC). | Complete
99 | RATE UPDATE | COVID UPDATES : Rate Increase for Intermediate Care Facilities (ICF) | Designated Intermediate Care Facilities | On 3/30/2020, HFS released temporary rate increase for certain Intermediate Care Facilities expenses associated with the COVID-19 pandemic | System configuration complete late August 2020. No claims impact. | Complete
85 | PROCESSING ERROR | MPA/MHVA Rate Year 2020 Add ons not paying on claims Remark Code: n/a | Stand Alone Psychiatric and Rehab Facilities | Claims incorrectly pricing without approved MPA/MHVA add-ons for provider types 21 and 22 (psych and rehab facilities) | System configuration complete Claims reprocessing complete | Complete
88 | RATE UPDATE | HFS Rate Update: Revised Hospital and Safety Net Rates Effective 10/1/2019 | Appealed Hospital Providers | Updated rates for hospitals based on appeals. | System configuration complete Claims reprocessing complete | Complete
93 | RATE UPDATE | HFS Rate Change: New Outpatient Rates effective 7/1/2020 | ALL Providers | On 6/25/2020 HFS released New Outpatient Rates effective 7/1/2020. | System configuration complete Claims reprocessing complete | Complete
94 | RATE UPDATE | HFS Updated IP and OP Hospital Rate Calculators | ALL Providers | On 6/26/2020 HFS released updated IP and OP Hospital rate calculators | System configuration complete 7/26/20 Claims reprocessing complete | Complete
54 | PROCESSING ERROR | Professional Services Rendered during Observations Stays Possible Remark Codes: S2, OS2; M62, CO-197 | Professional Providers | Receiving reports that professional services rendered while member is part of Observation stay are denying for no prior authorization. Obs stays do not require authorization, therefore these services also do not require authorization. | Under review. Once review complete will determine ETA for fix, should fix re required. System script fix for ancillary/professional denials during stays underway. Fixing issues as identified or notified by providers. System resolution complete | Complete
82 | RATE UPDATE | RATE UPDATE - PT per diem rates Effective Date: 8/7/2019 | Therapy Providers | On 4/16/20, HFS Released retro rate updates effective for DOS 8/7/2019 and after physical therapy per diem services. | System configuration complete Claims reprocessing complete | Complete
89 | RATE UPDATE | HFS Rate Update: Revised Hospital Inpatient and Outpatient Calculators | Hospitals | On 6/3/20, HFS released retro EAPG and DRG calculators (effective 10/1/2019 DOS and after) | System configuration complete Claims reprocessing complete | Complete
95 | RATE UPDATE | HFS Rate Update: Emergency Ambulance Rates | Emergency Ambulance Providers | On 6/27/2020 HFS released updated rates for public and private emergency ambulance rates | System configuration complete Claims reprocessing complete 11/4/2020 | Complete
96 | PROCESSING ERROR | FQHC FFS billing edit incorrectly flagging on non-FQHC claims Remark code: XI44 | Non-FQHC PCPs | Subset of claims potentially denying incorrectly for invalid billing taxonomy for non-FQHC providers, however edit is not relative to non-FQHCs: Rendering provider taxonomy billed is required as the billing provider taxonomy | System configuration complete Claims reprocessing complete 11/16/2020 | Complete
100 | RATE UPDATE | COVID: Designated facilities/units for testing and treatment | Designated LTC Facilities | On 4/28/2020, HFS released enhanced payments per day for isolation and ventilator services for individuals in COVID designated facilities/units. | System configuration complete | Complete
104 | RATE UPDATE | HFS Rate Update: LTC Rates and SLF Rates effective 7/1/2020 | LTC, SLF Providers | On 7/31/2020, HFS released LTC and SLF rates effective 7/1/2020 | System configuration complete 9/11/2020 Claims reprocessing complete 10/13/2020 | Complete
105 | RATE UPDATE | HFS Rate Update: SUPR FY 2021 (effective 7/1/2020) | SUPR/DASA Providers | On 8/2/2020 HFS released SUPR FY2021 rate updates | System configuration complete 9/11/2020 Claims reprocessing complete 10/18/2020 | Complete
106 | RATE UPDATE | Hospital Rate Calculators (effective 07/01/2020) | Hospitals | On 8/31/2020 HFS released Hospital Rate Calculators effective 07/01/2020 | System configuration complete 10/9/2020 Claims reprocessing complete 10/18/2020 | Complete
107 | RATE UPDATE | FY21 CBS Rate Sheet (effective 07/01/2020) | Behavioral Health Providers | On 9/2/2020 HFS released FY21 CBS rate updates for community behavioral health providers effective 7/1/2020 | System configuration complete 10/9/2020 Claims reprocessing complete 10/12/2020 | Complete
111 | PROGRAM UPDATE | Atypical Billing - New HFS Billing Guidelines | Waiver/Atypical Providers | HFS released guidance for atypical billing - mainly must use HFS Provider Number and must NOT use NPI - for billing atypical services effective 11/1/2020 received dates. | System configuration complete as of 11/1/2020 | Complete
112 | RATE UPDATE | HFS Rate Update: SUPR "Grandfathered" Rates | SUPR/DASA Providers | On 9/18/2020 HFS released revised DASA/SUPR rates for DASA/SUPR providers | System configuration complete Claims reprocessing complete as of 10/18/2020 | Complete
115 | RATE UPDATE | HFS Rate Change: Long Term Care, Effective 07.01.2019 | LTC, SMHRF, SLF Providers | On 9/28/2020 HFS released retro LTC Fee Schedule updates effective 07/01/2019 | System configuration complete Claims reprocessing complete as of 11/20/2020 | Complete
117 | RATE UPDATE | HFS Rate Change: IL HFS Medicaid Reimbursement Fee Schedule Renal Dialysis, Effective 05/22/2020 | ALL Providers | On 10/2/2020 HFS released Renal Dialysis Fee Schedule updates effective 05/22/2020 | System configuration complete Claims reprocessing complete as of 10/27/2020 | Complete
119 | RATE UPDATE | HFS Rate Change: NF/SLP Rates, Effective Date 10/01/2020 | LTC, SMHRF, SLF Providers | On 10/9/2020 HFS released SNF/SLP Fee Schedule updates effective 10/01/2020 | System configuration complete Claims reprocessing complete as of 11/13/2020 | Complete
72 | PROCESSING ERROR | Surgical Add Ons / Consultative Add Ons Remark Code: n/a | Surgical Providers | HFS clarification received 1/27/20: Applicable to any provider/COS allowed to bill surgical procedure codes for office POS | System configuration complete Claims reprocessing complete 12/18/2020 | Complete
108 | RATE UPDATE | HFS Rate Update: Practitioner Fee Schedule (effective 07/01/2020) | ALL Providers | On 9/10/2020 HFS released practitioner fee schedule updates effective 07/01/2020. Includes 60% Medicare rate update for specific provider types. | System configuration complete Reprocessing complete 12/20/2020 | Complete
118 | RATE UPDATE | HFS Rate Change: LTAC Retro Rate Sheets, (Quarterly) Multiple Effective Dates | LTAC Providers | On 10/9/2020 HFS released retro LTAC Fee Schedule updates | System configuration complete Claims reprocessing complete | Complete
122 | PROGRAM UPDATE | Applied Behavior Analysis (ABA) Services & Coverage - Effective 11/01/2020 | Approved Providers | On 10/29/2020, HFS announced new Applied Behavior Analysis (ABA) services and coverage guidelines effective November 1, 2020. | System configuration complete 12/1/2020 No claims impacted | Complete
91 | PROGRAM UPDATE | HFS Policy Change: Hospital Professional Billing Transition to the Outpatient Institutional Claim | ALL Providers | On 6/3/20, HFS released billing guidance for all hospital professional billing to be included on UB claim form as of 7/1/2020. All FFS must be billed with institutional NPI. | System configuration complete Reprocessing complete 12/31/2020 | Complete
110 | PROCESSING ERROR | DASA/SUPR Claims Denying for Invalid Taxonomy Remark Code: XI94 | SUPR/DASA Providers | MAT taxonomy must be billed for MAT services and may not be billed for any other services - reviewing claims where providers have indicated did NOT bill MAT taxonomy for non MAT services and believe denial is not accurate (in these cases). | System configuration complete Reprocessing complete 12/31/2020 | Complete
113 | RATE UPDATE | HFS Rate Change: DME Fee Schedule - Effective 01/01/2020 | DME Providers | On 9/16/2020 HFS released DME Fee Schedule updates effective 01/01/2020 | System configuration complete Reprocessing complete 12/30/2020 | Complete
114 | RATE UPDATE | HFS Rate Change: SUPR Rate Sheet - Effective 09/01/2020 | SUPR/DASA Providers | On 9/17/2020 HFS released SUPR Fee Schedule updates effective 09/01/2020 | System configuration complete Reprocessing complete 1/29/2021 | Complete
120 | RATE UPDATE | HFS Rate Change: Medicaid Reimbursement Fee Schedule (Rate Change): ACR, Effective Date 09/01/2020 | UIC SIU | On 10/20/20, HFS Released retro rate updates effective for RY2021 beginning with DOS 9/1/2020 and after for UIC and SIU. | System configuration complete Reprocessing complete 12/30/2020 | Complete
123 | RATE UPDATE | IL HFS Medicaid Reimbursement Fee Schedule (Rate Change): Ambulance Provider Rate, Effective Date 10/06/2020 | In State Ambulance Providers (Public and Nonpublic) | On 11/9/2020 HFS released an update rate sheet for In State Ambulance Providers effective 10/06/2020 | System configuration complete Reprocessing complete 1/22/2021 | Complete
125 | PROCESSING ERROR | Adjustments with clearinghouse edits | ALL Providers | Early November front end edits for claim level details were erroneously turned on that were not previously in place. All edits are in process of being relaxed by end of November. Claims will be reprocessed. | System configuration complete Impacted claims reprocessed 12/15/2020 | Complete
126 | RATE UPDATE | IL HFS Medicaid Reimbursement Fee Schedule (Rate Change): Gender Affirming Services | ALL Providers | On 11/9/2020, HFS provided clarification on gender affirming services and frequently billed codes 11/16/2020 | System configuration complete | Complete
127 | RATE UPDATE | Updated HFS Rate Change: Practitioner Fee Schedule, Effective 07/01/2020 | ALL Providers | On 11/16/2020, HFS released an update to the 7/1/2020 Practitioner Fee Schedule for correction to CPT codes 99214 and 99215 base rate and add ons | System configuration complete Impacted claim review in progress | In progress
128 | RATE UPDATE | IL HFS Medicaid Reimbursement Fee Schedule (Rate Change): Retro Rate Sheets for LTC Facilities | LTC Providers | On 11/19/2020, HFS released Retro rate sheets for LTC facilities | System configuration complete Reprocessing complete 12/29/2020 | Complete
131 | RATE UPDATE | IL HFS Medicaid Reimbursement Fee Schedule (Rate Change): ACR to Directed Payments Transition, Effective for DOS 01/01/2021 | UIC SIU | On 12/3/2020, HFS shared that facilities receiving ACR will be moved to standard Medicaid rates effective 1/1/2021 | System configuration complete | Complete
132 | RATE UPDATE | IL HFS Medicaid Reimbursement Fee Schedule (Rate Change): Illinois Medicaid COVID-19 Fee Schedule, UPDATE as of 12/4/2020 | ALL Providers | On 12/4/2020, HFS added a new section to the COVID-19 fee schedule with antibody and treatment pricing | System configuration complete | Complete
134 | PROCESSING ERROR | High Dollar Drug Underpayments | Hospitals | High Cost Drug/Device Add On payments not applying to applicable claims | System configuration complete Reprocessing complete 1/22/2021 | Complete
137 | RATE UPDATE | IL HFS Medicaid Reimbursement Fee Schedule (Rate Change): Rural Health Clinic Rates for CY 2021 | Rural Health Clinics | On 12/22/2020, HFS provided CY2021 Rural Health Clinic rates | System configuration complete Claims reprocessing complete | Complete
136 | RATE UPDATE | COVID-19 Vaccinations: IL HFS Update | ALL Providers | On 12/18/2020, HFS provided COVID-19 vaccine rates | System configuration complete Claims reprocessing complete | Complete
116 | RATE UPDATE | HFS Rate Change: 2021 MPA MHVA Rates - Before Appeal, Effective 10/01/2020 - 09/30/2021 | ALL Providers | On 10/2/2020 HFS released RY2021 MPA MHVA Rates Fee Schedule updates effective 10/01/2020 | System configuration complete Reprocessing complete 1/29/2021 | Complete
121 | RATE UPDATE | HFS Rate Change: Medicaid Reimbursement Fee Schedule (Rate Change): CBS UPDATE | Behavioral Health Providers | On 10/20/2020 An HFS error was identified on the rates for HCPCS H0039 and Q3014 from the previous CBS Rate Update effective 7/1/2020 | System configuration complete Reprocessing complete 1/22/2021 | Complete
138 | RATE UPDATE | IL HFS Medicaid Reimbursement Fee Schedule (Rate Change): FQHC Rates for Calendar Year 2021 | FQHCs | On 12/29/2020, HFS provided CY2021 FQHC rates | System configuration complete Claims reprocessing complete as of 2/12/2021 | Complete
139 | RATE UPDATE | IL HFS Medicaid Reimbursement Fee Schedule (Rate Change): LTC Rates and SLF Rates for 01/01.21 | LTC, SMHRF, SLF Providers | On 1/8/2021 HFS released LTC and SLF rate updates effective 1/1/2021 | System configuration complete | Complete