## Open
ID | Open Date | Project | Provider Type | Inquiry Type | Description | Effective Date | Configuration Status | Config Ticket Completion Date | Claims Status | Claims Ticket Completion Date | Impacted Claim Start Date | Impacted Claim End Date
24 | 2024-10-22 | Hospice Annual Rate Changes | Hospice | HFS Inquiry | HFS submitted hospice rate updates effective 10/1/2024. All rates have been loaded. Pricing issue being tracked seperatly. | 2024-10-01 | In-Progress |  | Waiting for Configuration
67 | 2024-10-23 | Hospice Underpayments | Hospice | Global Issue | Hospice claims are under review that are pricing revenue code 0651 incorrectly. This is only affecting this revenue code and not all hospice claims. |  | In-Progress |  | Waiting for Configuration
87 | 2025-07-25 | XG01 firing on add on codes | Physicians | Global Issue | XG01 remark is firing on claims billed with add on codes. Remark descriptions states another E&M code was billed on the same date and requires modifier 25. Due it being an add on code, the 25 modifier should not be required for both codes to pay. |  | Complete | 2025-12-17 | In Progress
133 | 2025-08-13 | MAT Code H0020 Netting $0 | SUPR | Global Issue | Corrected claims billed with H0020 for MAT services are not pricing when billed within guidelines. Original denial is XB05 and after corrected are netting $0 with MX remark. Only isolated to providers sbmitted corrected claims for code H0020. |  | In-Progress |  | Waiting for Configuration
93 | 2025-08-14 | XQ84 Denial firing incorrectly on ABS Services | BHC | Global Issue | XQ84 denying incorrectly on ABS services when billed from a Behavioral Health Clinic. |  | In-Progress |  | Waiting for Configuration
95 | 2025-08-14 | 2025 Nursing Facility Per Diem Rate Updates | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted updated rates between May and July 2025 to certain LTC Facilities. Updates included appeals, capital, support, nursing rates, and some quarterly changes. |  | Complete | 2025-11-11 | In Progress
94 | 2025-08-18 | SNF/County/SMHRF/SLP MCO Rates Effective 7/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted updated rates for SNF/County/SMHRF/SLP effective 07/01/2025. This is an additional update from prior version received. |  | Complete | 2025-11-07 | In Progress |  | 2025-07-01 | 2025-09-30
110 | 2025-09-22 | Practitioner Fee Schedule Effective 7/1/2025 | Physicians | HFS Inquiry | HFS updated the Practitioner Fee Schedule effective 7/1/2025 |  | Complete | 2025-10-16 | In Progress |  | 2025-04-01 | 2025-09-25
112 | 2025-09-26 | Nursing Facility Per Diem Rate Update Effective 7/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted updates to the facilities nursing rate utilization add-ons and staffing add-ons effective 7/1/2025. |  | Complete | 2025-12-04 | In Progress |  | 2025-07-01 | 2025-11-21
117 | 2025-10-08 | SMHRFs Facility Rates Updates Effective 7/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted updated SMHRF rates effective 7/1/2025. Prior notification sent out had incorrect rates included. |  | Complete | 2025-11-07 | In Progress |  | 2025-07-01 | 2025-09-30
119 | 2025-10-09 | Professional Therapy Pricing Incorrect | Therapy | Global Issue | Professinal claims billed with PT/OT/ST are pricing with different rates. Pricing in review. Not affecting all therapy claims. |  | In-Progress |  | Waiting for Configuration
134 | 2025-11-04 | Waiver Rate Updates Effective 1/1/2026 | Waiver | HFS Inquiry | HFS submitted rate updates 3 DRS waiver services effective 1/1/2026 | 2026-01-01 | In-Progress |  | Waiting for Configuration
135 | 2025-11-18 | Renal Dialysis Add-on Payment Update Effective 1/1/2025 | Dialysis | HFS Inquiry | HFS updated guidance on the renal dialysis add ons effective 1/1/2025. Expanding coverage to additional dialysis revenue codes. |  | Complete | 2025-11-27 | In Progress | 2025-11-25 | 2025-01-01 | 2025-11-25
147 | 2025-11-19 | Remark XC35 firing on Diabetes Prevention Program Codes | Physicians | Global Issue | XC35 remark is incorrectly firing on claims billed as telehealth. Telehealth billing is allowed for these services. |  | In-Progress |  | Waiting for Configuration
148 | 2025-11-19 | X998 Firing Incorrectly on Diabetes Prevention Program Codes | Physicians | Global Issue | X998 is firing incorrectly when billed correctly with billing taxonomy |  | In-Progress |  | Waiting for Configuration
155 | 2025-11-24 | Implementation of New Claim Edits for Attending Provider | SNF/LTC/SMHRF/SLF | HFS Inquiry | The Attending Provider NPI field is required for all long term care (LTC) claims. Effective with dates of service on and after January 1, 2026, the Department will reject claims if the Attending Provider is not enrolled with the Department on the date of service. | 2026-01-01 | No Configuration Required |  | Waiting for Configuration
146 | 2025-12-08 | Updated LTC and SLP Rates Effective 10/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS updated the rates for LTC and SLP facilities effective 10/1/2025 | 2025-12-01 | In-Progress |  | Waiting for Configuration
140 | 2025-12-11 | 2026 FQHC Rates | FQHC/ERC/RHC | HFS Inquiry | HFS updated FQHC rate effective 1/1/2026 | 2026-01-01 | New |  | Waiting for Configuration
145 | 2025-12-12 | Home Visiting Organization Enrollment and Billing Effective 11.21.2025 | Physicians | HFS Inquiry | Medicaid Coverage for Home Visiting Services – Provider Enrollment and Billing Guidance (Effective November 21, 2025) | 2025-11-21 | New |  | Waiting for Configuration
149 | 2025-12-19 | Air Ambulance Paying Incorrectly | Air Ambulance | Global Issue | Air ambulance claims incorrectly pricing for service dates in 2025 |  | In-Progress |  | Waiting for Configuration
150 | 2025-12-22 | 2026 Rural Health Clinic (RHC) Rates | FQHC/ERC/RHC | HFS Inquiry | HFS updated medical rates for recently attested Rural Health Clinic (RHC) Rates for 2026 calendar year. | 2025-12-22 | In-Progress |  | Waiting for Configuration
151 | 2025-12-22 | MPA and MHVA Rates – Effective 01/01/2026 | Physicians | HFS Inquiry | The final 2026 MPA (Medicaid Perinatal Add-on) and MHVA (Mental Health Value Add) rates, which will be effective from January 1, 2026. | 2025-12-22 | In-Progress |  | Waiting for Configuration
152 | 2025-12-30 | Observation code G0379 pricing in error | Hospital | Global Issue | Observation code G0379 should always price $0 when billed with G0378 per IAMHP guidelines. Line is now pricing additional dollars on claims in error. |  | In-Progress |  | Waiting for Configuration
154 | 2026-01-05 | SLF LOA Days Overpaying per 30-day yearly cap | SNF/LTC/SMHRF/SLF | Global Issue | SLFs should only receive a total of 30 payable LOA days per fiscal year (July-June). Claims are pricing more than 30 days incorrectly. |  | New |  | Waiting for Configuration

## Closed
ID | Open Date | Project | Provider Type | Inquiry Type | Description | Effective Date | Configuration Status | Config Ticket Completion Date | Claims Status | Claims Ticket Completion Date | Impacted Claim Start Date | Impacted Claim End Date
136 | 2025-11-18 | Hospice Annual Rate Changes Effective 10/1/2025 | Hospital | HFS Inquiry | HFS updated Hospice rates effective October 1, 2025, through September 30, 2026. | 2025-10-01 | Complete | 2025-12-22 | Complete | 2025-12-30
126 | 2025-10-31 | MORP& RPNE Incorrectly firing on professional claims | Physicians | Global Issue | Professional claims incorreclty denying MORP & RPNE for services not requiring an ordering/referring provider. Reprocessing in progress |  | No Configuration Required |  | Complete | 2025-12-12
38 | 2025-05-05 | Claims denying X165 | Physicians | Global Issue | Claims are denying X165 for incorrect primary DX code being used. Additional review in progress on ensuring edit is editing appropriatly from what was billed. |  | Complete | 2025-11-21 | Complete | 2025-12-03 | 2024-05-19 | 2025-11-19
63 | 2025-06-11 | Macneal Hospital- Rate update | Hospital | HFS Inquiry | HFS confirmed Macneal Hospital should receive rehab rate for COS 029 effective 4/1/2025 | 2025-04-01 | Complete | 2025-10-24 | Complete | 2025-12-02 | 2025-04-01 | 2025-07-31
92 | 2025-08-12 | SLP Rates Effective 4/1/25 underpaying | SNF/LTC/SMHRF/SLF | Global Issue | Two rate sheets received from HFS for 4/1/25 SLP rates. The incorrect one was loaded. In progress to upload the correct rates for SLP providers and reprocess claims. |  | Complete | 2025-10-17 | Complete | 2025-12-02 | 2025-08-14 | 2025-09-18
41 | 2025-04-29 | Practitioner Fee Schedule Updates Effective 1/1/2025 | Physicians | HFS Inquiry | Received HFS notice with updated practitioner fee schedule effective 1/1/2025 | 2025-01-01 | Complete | 2025-07-08 | Complete | 2025-12-01 | 2025-01-01 | 2025-06-13
107 | 2025-09-22 | COVID-19 Fee Schedule Update Effective 7/1/2025 | Physicians | HFS Inquiry | HFS updated the COVID-19 fee schedule effective 7/1/2025. Codes updated 91304, 91320, 91323. Removal of codes 0240U & 0241U. |  | Complete | 2025-11-21 | Complete | 2025-11-28 | 2025-08-27 | 2025-10-28
108 | 2025-09-22 | CCBHC Rate Updates Effective 10/1/2025 | CCBHC | HFS Inquiry | HFS submitted udpated rates for CCBHC Clinics Effective 10/1/2025. |  | Complete | 2025-11-12 | Complete | 2025-11-28 | 2025-10-01 | 2025-10-27
114 | 2025-10-03 | XP64 Early Delivery Denial In Error | Hospital | Global Issue | XP64 dening incorrectly on diagnosis code O99.52. This diagnosis code is eligible for early deliveries. Reviewing list of all early delivery diagnosis codes to ensure they align with notices. |  | Complete | 2025-11-26 | Complete | 2025-11-28 | 2024-05-10 | 2025-11-26
73 | 2025-06-26 | 2025 DME Fee Schedule | DME | HFS Inquiry | HFS udpated DME Fee Schedule Update Effective 1/1/2025 | 2025-01-01 | Complete | 2025-10-23 | Complete | 2025-11-27 | 2025-01-01 | 2025-06-01
91 | 2025-08-01 | SIA (service intensity add on) not pricing on hospice claims | Hospice | Global Issue | Service intensity add on payments for rev codes 055X and 056X are not pricing on claims when billed correctly per hospice guidelines |  | Complete | 2025-11-14 | Complete | 2025-11-25 | 2025-03-24 | 2025-09-25
109 | 2025-09-22 | Doula fee schedule Updated 9/22/2025 | Doula | HFS Inquiry | HFS updated the Doula Fee Schedule Effective 9/22/2025 |  | Complete | 2025-11-21 | Complete | 2025-11-24 | 2024-01-01 | 2025-11-04
101 | 2025-09-04 | Claims Denying with Remark X161 | Physicians | Global Issue | Claims are denying with remark X161 (The DX code is invalid or disabled). Updates in progress for those claims incorrectly receiving remark. Isolated to hospice and long term care claims. |  | Complete | 2025-11-14 | Complete | 2025-11-21 | 2025-09-02 | 2025-09-09
116 | 2025-10-08 | DME Fee Schedule Codes Updated 4/1/25 per HFS Key | DME | Global Issue | 3 codes were called out on the DME Fee Schedule key with changes effective 4/1/25 and not 1/1/25. Codes L8010, A4453, & A4459 need reviewed to determine correct effective date of changes were updated within the system. |  | Complete | 2025-11-19 | Complete | 2025-11-19 | 2025-01-01 | 2025-03-31
103 | 2025-09-09 | Podiatrist Fee Schedule Effective 4/1/2025 | Physicians | HFS Inquiry | HFS updated Podiatry Fee Schedule Effective 4/1/25 | 2025-04-01 | Complete | 2025-10-01 | Complete | 2025-11-17 | 2025-04-01 | 2025-08-29
120 | 2025-10-09 | Doulas Claims not pricing | Doula | Global Issue | Doula claims not pricing when billed correctly and provider registration aligns. These claims netting $0 with an MX remark code in error. |  | Complete | 2025-11-17 | No impacted claims | 2025-11-17
124 | 2025-10-27 | SNF/County/SMHRF/SLP MCO Rates Effective 10/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS updated LTC rates effective 10/1/25. Per HFS, updated rates forthcoming | 2025-10-01 | No Configuration Required | 2025-11-07 | No impacted claims | 2025-11-07
78 | 2025-07-01 | Updated APR-DRG and EAPG Hospital Rate Calculators Effective 4/1/2025 | Hospital | HFS Inquiry | HFS updated the most recent APR-DRG and EAPG rates effective 4/1/2025. | 2025-04-01 | Complete | 2025-10-17 | Complete | 2025-11-05 | 2025-04-01 | 2025-07-31
111 | 2025-09-26 | Podiatry Fee Schedule Update Effective 9/1/2025 | Podiatrist | HFS Inquiry | HFS submitted updates to the Podiatry Fee Schedule effective 9/1/2025. Updates only pertain to codes 11981 & 11982. |  | Complete | 2025-11-04 | No impacted claims | 2025-11-04
52 | 2025-05-21 | Preventive Visit and Female Annual Exam Visit within a year allowed | Physicians | Global Issue | 1PYM Firing in error on preventive female visit billed within the same year as a regular preventive visit. Practitioner handbook allows both within the same benefit period. |  | Complete | 2025-09-01 | Complete | 2025-10-30 | 2024-06-02 | 2025-08-06
122 | 2025-10-14 | Pend WNC denials for review | Waiver | Global Issue | Moving WNC denial to a pend queue for manual review. To mitigate abrasion we are requesting that Waiver claims be pended to a queue and a manual review occur to confirm if the member has an active service plan on the date of service |  | Complete | 2025-10-20 | No impacted claims | 2025-10-20
104 | 2025-09-09 | School Based Health Services Fee Schedule | Physicians | HFS Inquiry |  | 2025-04-01 | Complete | 2025-10-17 | No impacted claims | 2025-10-17
102 | 2025-09-04 | XA16 (CBS CANNOT BE DETERMINED FOR THIS CLAIM) firing on incorrect hospice rev code 658 | Hospice | Global Issue | XA16 is incorrectly denying on hospice rev code 0658. This revenue code does not apply CBSA Wage Component pricing. |  | Complete | 2025-10-10 | Complete | 2025-10-14
64 | 2025-06-06 | X3 Denial on Valid Codes | Hospital | Global Issue | Edit is currently denying claims with remark X3 for valid principal procedure codes billed. |  | Complete | 2025-09-01 | Complete | 2025-10-08
125 | 2025-10-31 | MORP Denying Incorrectly for Waiver Services | Waiver | Global Issue | MORP incorrectly denying on waiver codes. Ordering and referring providers not required on these services. Updates in progress along with reprocessing. |  | No Configuration Required | 2025-09-25 | Complete | 2025-09-29
79 | 2025-06-30 | X403 Denial Review | Hospital | Global Issue | Claims are denyin X403 for ER services. Remark description: Claim does not contain the appropriate ER, observation or psychiatric clinic services for Illinois Medicaid. These are APL claim requirements that are no longer required. |  | Complete | 2025-09-19 | Complete | 2025-09-22
83 | 2025-07-18 | Nursing Facility Per Diem Rate Notices | SNF/LTC/SMHRF/SLF | HFS Inquiry | Attached are two Rate sheets, with the first attachment having several facilities within. All are changes due to appeals. 1) BLTC-BRDA PDF RATE SHEETS - NOT QTRLY (retro, capital, other) · 6012827 AVANTARA OF ELGIN · 6012553 BELLA TERRA SCHAUMBURG · 6014195 WARREN BARR BUFFALO GROVE · CITADEL OF GLENVIEW, THE | 2025-04-01 | Complete | 2025-08-22 | Complete | 2025-09-19
89 | 2025-07-31 | Remove Oxygen from MLTSS Benefit Coverage | DME | Global Issue | Oxygen code E1390 is not covered by the state for MLTSS members. Update to configuration needed to ensure it denies if billed. |  | Complete | 2025-08-13 | Complete | 2025-09-12 | 2024-08-12 | 2025-08-12
86 | 2025-07-25 | Professional Psych claim paying over billed charges | Physicians | Global Issue | Psych Professional Claims paying over billed amount in error and not capping at billed charges. |  | Complete | 2025-09-08 | No impacted claims | 2025-09-08
90 | 2025-08-01 | T1505 Denying MLTSS in error | Waiver | Global Issue | T1505 is denying MLTS in error when waiver code is within benefit. |  | Complete | 2025-08-14 | Complete | 2025-09-03 | 2024-02-13 | 2025-08-13
82 | 2025-07-18 | Outpatient Therapy Codes applying hand pricing methdology in error | Therapy | Global Issue | Outpatient home health therapy codes are applying hand pricing methodology in error instead of fee schedule pricing. |  | Complete | 2025-08-07 | Complete | 2025-08-29 | 2025-06-13 | 2025-07-21
99 | 2025-08-20 | Remove the PLH hold for Planned Parenthood 362170901 |  | HFS Inquiry | Per guidance received from HFS today please remove the PLH hold from TIN 362170901 Per HFS we can resume claims payment for all dates of service effective immediately. |  | Complete | 2025-08-29 | No impacted claims | 2025-08-29
42 | 2025-05-16 | CMHC Codes denying for MLTSS Members | CMHC | Global Issue | Claims are denying MLTS for CMHC Codes for MLTSS members in error. Providers registered for COS 047 & 34 are eligible to bill for MLTSS services. |  | Complete | 2025-08-04 | Complete | 2025-08-20 | 2024-01-25 | 2025-07-25
98 | 2025-08-14 | ALTON MEMORIAL HOSPITAL | Hospital | HFS Inquiry | Although the latest hospital calculators contain the correct rate information, attached is the corresponding correct rate sheet for Alton Memorial Hospital. |  | No Configuration Required | 2025-08-19 | No impacted claims | 2025-08-19
31 | 2025-04-24 | Code 90837 paying in error when billed by CMHC | CMHC | Global Issue | Procedure code 90837 identified as incorrectly paying when billed by a CMHC provider. Code not payable per CMHC billing fee schedule. |  | Complete | 2025-07-25 | Complete | 2025-08-14
62 | 2025-06-09 | Montrose Hospitals MHVA/MPA | Hospital | HFS Inquiry | HFS sent incorrect add ons for Adult and Childrens facility. Per confirmation from HFS in this ticket, we have recieved the correct add on rates for MPA/MHVA. Recalc will be requried to adjust under and overpayments. | 2025-01-01 | Complete | 2025-07-31 | Complete | 2025-08-07 | 2025-01-01 | 2025-07-16
68 | 2025-06-23 | Incorrect S2 Therapy Denials | Therapy | Global Issue | Requesting report for all S2 denials on therapy codes with date of service 3/1/25 to current. Claims incorrectly denied with authorization will be reprocessed. |  | No Configuration Required |  | Complete | 2025-08-06
53 | 2025-05-27 | Licensed Practitioner of the Healing Arts Fee schedule | Physicians | HFS Inquiry | HFS updated LPHA Fee Schedule Effective 01/01/2025 | 2025-01-01 | Complete | 2025-06-13 | Complete | 2025-07-28 | 2025-01-01 | 2025-05-21
54 | 2025-05-14 | SNF/SMHRF/SLP MCO Rates | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS updated SNF, SMHRF and SLP rates effective 04/01/2025. | 2025-04-01 | Complete | 2025-06-18 | Complete | 2025-07-23 | 2025-04-01 | 2025-06-04
44 | 2025-05-14 | Renal Dialysis Add-on Payment | Dialysis | HFS Inquiry | HFS updated new $95 Dialysis Add on payment for free standing dialysis centers treating members in LTC facility for home dialyis rev codes 841 & 851 | 2025-05-01 | Complete | 2025-06-24 | Complete | 2025-07-22
59 | 2025-06-03 | Additional Practitioner fee schedule update Effective 1/1/2025 | Physicians | HFS Inquiry | HFS made additional update to the practitioner fee schedule effective 1/1/25 with missing codes 87564, 87594, & 876265 | 2025-01-01 | Complete | 2025-06-18 | Complete | 2025-07-22 | 2025-01-01 | 2025-06-06
81 | 2025-07-15 | XQ07 Firing on ABS Services | Physicians | Global Issue | Claims incorrectly denying XQ07 when billed correctly for ABS services. |  | No Configuration Required | 2025-07-15 | Complete | 2025-07-15
11 | 2024-11-06 | Psych Add Ons not applying on Physician claims | Physicians | Global Issue | Psych add ons are incorrectly not applying to physicians who are registered with psychiatric specialty on IMPACT file. |  | Complete | 2025-06-02 | Complete | 2025-07-11
35 | 2025-04-29 | Waiver Code T1505 not assigned rate | Waiver | Global Issue | Claims billed with waiver code T1505 are not pricing per waiver fee schedule. |  | Complete | 2025-06-09 | Complete | 2025-07-11 | 2023-11-27 | 2025-05-27
48 | 2025-05-19 | Optometric Fee Schedule | Physicians | HFS Inquiry | HFS udpated Optometric Fee Schedule Effective 01/01/2025 | 2025-01-01 | Complete | 2025-06-03 | Complete | 2025-07-04 | 2025-01-01 | 2025-05-22
58 | 2025-06-03 | DRS waivers updates 7/1/25 Rate | Waiver | HFS Inquiry | CMS approval received for waiver rate updates effective 7/1/25 | 2025-07-01 | Complete | 2025-06-26 | No impacted claims | 2025-06-26
30 | 2025-04-28 | FQHC Claims Paying with no detail codes | FQHC/ERC/RHC | Global Issue | FQHC claims require detail code to be payable. Claims received with no detail code were allowing payment incorrectly. |  | Complete | 2025-06-13 | Complete | 2025-06-25 | 2024-05-13 | 2025-05-13
2 | 2025-03-27 | Therapy & Evaluation not pricing on the same date Effective 12/1/2024 | Hospital | Global Issue | Per HFS, therap and evaluations are both reimburseable on the same date as of 12/1/24. Configuration not setup correctly to price both services. |  | Complete | 2025-05-16 | Complete | 2025-06-23 | 2024-12-01 | 2025-04-21
14 | 2025-04-03 | SMHRF Reimbursement Changes | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS sent clarification on the SMHRF all inclusive per diem rate and which facilities it applies to | 2025-01-01 | Complete | 2025-05-12 | Complete | 2025-06-18 | 2025-01-01 | 2025-04-22
55 | 2025-05-29 | MMR Vaccination for Children | Physicians | HFS Inquiry | HFS posted notice for MMR Vaccination for Children Aged 6 through 11 Months effective May 5, 2025 | 2025-05-05 | Complete |  | Complete | 2025-06-17
10 | 2025-01-28 | Outpatient Dialysis paying incorrectly | Dialysis | Global Issue | Outpatient dialysis per diem pricing not applying to all dialysis revenue codes. Pricing defaulting to EAPG incorrectly. |  | Complete | 2025-06-05 | Complete | 2025-06-10
1 | 2025-03-28 | Code J8499 not hand pricing correctly | Physicians | Global Issue | Procedure code J8499 was not pricing per hand methodology correctly |  | Complete | 2025-06-06 | No impacted claims | 2025-06-06
13 | 2025-04-01 | Nursing Facility Per Diem Rate Notices - Capital Rate | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted capital rate updates for nursing facilities effective 1/1/2025 | 2025-01-01 | Complete | 2025-05-07 | Complete | 2025-06-06 | 2025-01-01 | 2025-04-25
21 | 2025-01-29 | Revised APR-DRG and EAPG Hospital Rate Calculators | Hospital | HFS Inquiry | Inpatient/Outpatient Hospital Rate Updates Effective 1/1/2025 | 2025-01-01 | Complete | 2025-04-15 | Complete | 2025-06-04 | 2025-01-01
8 | 2025-02-28 | Remove 6 Visit Claims Counting Rule for PT/OT ST | Physicians | Global Issue | Effective 3/1/25 all therapy visits require prior authorization for PT/OT/ST services. |  | Complete | 2025-05-06 | No impacted claims | 2025-05-06