## Open
ID | Open Date | Project | Provider Type | Inquiry Type | Description | Effective Date | Configuration Status | Config Ticket Completion Date | Claims Status | Claims Ticket Completion Date | Impacted Claim Start Date | Impacted Claim End Date
137 | 2025-12-05 | Review of Home Health Fee Schedule | Home Health | Global Issue | Requesting Zelis review how Home Health claim price per the fee schedule. IAMHP states only allowed to bill on 837I claim form. Claims are paying when billed on 837P professional claim form. |  | Complete | 2026-10-06 | In Progress |  | 2025-06-10 | 2026-06-10
207 | 2026-06-09 | APR-DRG and EAPG Hospital Rate Calculators Updates | Hospital | HFS Inquiry | HFS sent an additional update: APR-DRG and EAPG Hospital Rate Calculators Updates | 2026-01-01 | Complete | 2026-09-01 | In Progress |  | 2026-01-01 | 2026-07-17
212 | 2026-06-24 | EAPG Pricing Review | Hospital | Global Issue | We are currently doing some internal review and testing around ER/Observation/Lab claims. We are receiving various provider disputes of under and overpayments on these services. Providers are seeing differeng packing and pricing outcomes within their pricer. |  | In-Progress |  | Waiting for Configuration
216 | 2026-07-14 | SNF/County/SMHRF/SLP MCO Rates (NPI rate sheets) effective July 1, 2026 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS updated SNF/County/SMHRF/SLP MCO Rates (NPI rate sheets) effective July 1, 2026. | 2026-07-01 | Complete |  | In Progress |  | 2026-07-01 | 2026-08-13
218 | 2026-07-21 | Coding Update for Behavioral Health Screenings Effective August 1, 2026 | BHC | HFS Inquiry | Coding Update for Behavioral Health Screenings Effective August 1, 2026 | 2026-08-01 | In-Progress |  | Waiting for Configuration
219 | 2026-07-21 | Psych Add On not applying | Physicians | Global Issue | Psych add ons are not consisently applying to Nurse Practitioners registered correctly with Psychiatric and Mental Health nursing. |  | Complete | 2026-09-24 | In Progress
220 | 2026-07-28 | FQHC Front End Edit Update | FQHC/ERC/RHC | Global Issue | Updating our FQHC edit to ensure we only accept properly billed claims into our system. Edit udpate in progress to reject claims billed with FQHC taxonomies 261QF0400X OR 261QR1300X in the rendering field. This is a billing only taxonomy. |  | No Configuration Required |  | Waiting for Configuration
223 | 2026-07-30 | COVID-19 fee schedule effective 4/1/26 | Physicians | HFS Inquiry | HFS has updated COVID-19 fee schedule effective 4/1/26 | 2026-04-01 | In-Progress |  | Waiting for Configuration
226 | 2026-08-03 | SLP Add-On Payment Reinstatement for Quarter 2 and Quarter 3 | Hospital | HFS Inquiry | HFS updated SLP Add-On Payment Reinstatement for Quarter 2 and Quarter 3. | 2026-07-01 | Complete | 2026-10-07 | In Progress |  | 2026-04-01 | 2026-09-25
224 | 2026-08-04 | X218 Remark Firing in error on code 01968 | Physicians | Global Issue | Remark is incorrectly firing when primary procedure code 01967 is billed on another claim. Remark states: THE ADD-ON PROCEDURE CODE HAS BEEN SUBMITTED WITHOUT AN APPROPRIATE PRIMARY PROCEDURE. The primary procedure and add on code are not required on the same claim. |  | In-Progress |  | Waiting for Configuration
229 | 2026-08-18 | Practitioner Fee Schedule and PFS Key eff 07.01.26 | Physicians | HFS Inquiry | HFS has updated Practitioner Fee Schedule and PFS Key eff 07.01.26. | 2026-07-01 | In-Progress |  | Waiting for Configuration
230 | 2026-08-18 | COVID-19 fee schedule effective 7/1/2026 | Physicians | HFS Inquiry | HFS has updated COVID-19 fee schedule effective 7/1/2026 | 2026-07-01 | In-Progress |  | Waiting for Configuration
232 | 2026-08-18 | Home Visiting fee schedule effective 10/1/2025 | Home Health | HFS Inquiry | HFS has pdated Home Visiting fee schedule effective 10/1/2025 | 2025-10-01 | In-Progress |  | Waiting for Configuration
243 | 2026-08-25 | Hospital claims with revenue code 025X paying with missing NDC | Hospital | Global Issue | Per IAMHP claims submitted with a HCPC along with revenue code 025X require NDC validation per the practitioner fee schedule NDC field = to Y. Claims have been incorrectly paying when HCPC does require NDC code. |  | In-Progress |  | Waiting for Configuration
233 | 2026-09-01 | Updates APR-DRG and EAPG Hospital Rate Calculators Updates effective 01.01.26 | Hospital | HFS Inquiry | HFS has re-posted updated APR-DRG and EAPG Hospital Rate Calculators Updates effective 01.01.26. | 2026-01-01 | In-Progress |  | Waiting for Configuration
234 | 2026-09-03 | H0004 Claims Denying XQ02 | SUPR | Global Issue | H0004 is denying in error for XQ02 on claims that are billed correctly. |  | In-Progress |  | Waiting for Configuration
235 | 2026-09-03 | Podiatry Code L3000 not pricing | Podiatrist | Global Issue | Procedure code L3000 is billable for Podiatrists per the fee schedule. Claims are not pricing upon adjustment for this code. |  | In-Progress |  | Waiting for Configuration
237 | 2026-09-22 | Practitioner Fee Schedule effective 7/1/26 | Physicians | HFS Inquiry | HFS updated the Practitioner Fee Schedule effective 7/1/26 | 2026-07-01 | In-Progress |  | Waiting for Configuration
238 | 2026-09-22 | Doula Fee Schedule Effective 5/1/2026 | Doula | HFS Inquiry | HFS has updated Doula Fee Schedule Effective 5/1/2026 | 2026-05-01 |  |  | Waiting for Configuration
239 | 2026-09-22 | SLP Add-On Payment Suspension [for Quarter 4] Effective 10/1/2026 | Hospital | HFS Inquiry | HFS is removing a $2.75 add on quality payment for the SLP Add-On Payment Suspension [for Quarter 4] Effective 10/1/2026 | 2026-10-01 | In-Progress |  | Waiting for Configuration
240 | 2026-09-22 | SLP Add-On Payment Reinstatement [for Quarter 4] Effective 10/1/2026 | Hospital | HFS Inquiry | HFS is reinstating the add on quality payment for only the 3 SLP Add-On Payment Reinstatement [for Quarter 4] Effective 10/1/2026 | 2026-10-01 | In-Progress |  | Waiting for Configuration
241 | 2026-09-24 | FQHC Claims Denying with remark RQ50 & X870 | FQHC/ERC/RHC | Global Issue | Denials are both under review. Detail lines can be billed with $0 charges per IAMHP manual for Encounter claims. |  | In-Progress |  | Waiting for Configuration
242 | 2026-09-27 | OBPM Remark firing on Ultrasounds billed in the ER | Physicians | Global Issue | OBPM remark is firing incorrectly on ER claims. 3 visits are allowed prior to PA for ultrasounds but ER visit should not be included in this count. |  | In-Progress |  | Waiting for Configuration
245 | 2026-09-30 | SUPR code H2036 Underpaying per 7/1/25 Rate Updates | SUPR | Global Issue | SUPR code H2036 is underpaying per the 7/1/2025 fee schedule |  | In-Progress |  | Waiting for Configuration
247 | 2026-10-06 | Review of remark X994 on hospital claims | Hospital | Global Issue | Remark X994 fires with description: DRG FOR THIS CLAIM IS NOT DEFINED. Reviewing remark to confirm why the claim is pricing with DRG 955 when not submitted by the provider. |  | In-Progress |  | Waiting for Configuration

## Closed
ID | Open Date | Project | Provider Type | Inquiry Type | Description | Effective Date | Configuration Status | Config Ticket Completion Date | Claims Status | Claims Ticket Completion Date | Impacted Claim Start Date | Impacted Claim End Date
183 | 2026-03-31 | SNF/SMHRF/SLP Rates effective 4/1/2026 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS updated SNF/SMHRF/SLP rates effective 4/1/2026 | 2026-04-01 | Complete | 2026-06-24 | Complete | 2026-10-06 | 2026-04-01 | 2026-08-12
217 | 2026-07-14 | Practitioner Fee Schedule and PFS Key effective 04.01.26 | Physicians | HFS Inquiry | HFS has updated Practitioner Fee Schedule and PFS Key effective 04.01.26. | 2026-04-01 | Complete | 2026-09-21 | Complete | 2026-10-06 | 2026-04-01 | 2026-07-24
236 | 2026-09-03 | Updated to remark XQ22 for FQHC Claims | FQHC/ERC/RHC | Global Issue | Removing the claim level denial XQ22 for FQHC claims. Provider will only receive the line level XQ20 denial but not a denial on the entire encounter |  | Complete | 2026-09-15 | Complete | 2026-10-06 |  | 2026-09-08
204 | 2026-04-23 | Remark XK69 not firing on hospital claims | Hospital | Global Issue | Edit being updated to allow when rendering provider is not a hospital provider type 30-32. Global reprocessing project in progress |  | Complete | 2026-08-20 | Complete | 2026-10-05
209 | 2026-06-12 | 90677 denying XQ20 in error | Physicians | Global Issue | Minimum age for code 90677 is 6 weeks. Claims with members over 6 weeks of age are denying this line XQ20 in error. |  | Complete | 2026-08-31 | Complete | 2026-09-25 | 2025-02-11
213 | 2026-06-23 | SLP Add-On Payment Suspension for Quarter 2 and Quarter 3 | Hospital | HFS Inquiry | HFS Updated SLP Add-On Payment Suspension for Quarter 2 and Quarter 3. | 2026-04-01 | Complete | 2026-07-30 | Complete | 2026-09-25
197 | 2026-05-19 | Licensed Certified Professional Midwife Provider Type update | Hospital | HFS Inquiry | HFS updated Licensed Certified Professional Midwife Provider Type update. | 2026-05-01 | Complete | 2026-09-24 | No impacted claims | 2026-09-24
227 | 2026-08-03 | Two new modifiers for HCBS in home homemaker services-for MCOs | Physicians | HFS Inquiry | HFS updated Two new modifiers for HCBS in home homemaker services-for MCOs |  | Complete | 2026-09-17 | No impacted claims | 2026-09-17
182 | 2026-03-24 | SUPR service rates, effective 7/1/2025 | SUPR | HFS Inquiry | HFS updated SUD service rates, effective 7/1/2025 | 2025-07-01 | Complete | 2026-06-03 | Complete | 2026-09-15 | 2025-07-01 | 2026-06-03
211 | 2026-06-23 | SUPR Codes overpaying .01 cent when billed hourly | SUPR | Global Issue | HFS confirmed codes on the SUPR Rate sheet are already rounded to the nearest 100th. Current configuration has these codes rounding incorrectly causing .01 cents to overpay per hour on certain codes. |  | Complete | 2026-08-10 | Complete | 2026-09-15 | 2025-07-01 | 2026-07-25
231 | 2026-08-18 | Podiatric Fee Schedule effective 07.01.26 | Podiatrist | HFS Inquiry | HFS updated Podiatric Fee Schedule effective 07.01.26 | 2026-07-01 | Complete | 2026-09-15 | No impacted claims | 2026-09-15
205 | 2026-05-29 | 1/1/2026 Waiver Homemaker Rate underpaying | Waiver | Global Issue | The unit rate is rounding down by .01 cent and is causing small underpayments. Unit rate is paying $8.14 and should be considered $8.1425 to get to the full hour rate of $32.57. |  | Complete | 2026-08-20 | Complete | 2026-09-02 | 2026-01-01 | 2026-06-22
221 | 2026-07-30 | School Based/Linked Health Center (SBLHC) Fee Schedule Effective 4.01.26 | Physicians | HFS Inquiry | HFS hsas updated School Based/Linked Health Center (SBLHC) Fee Schedule Effective 4.01.26 | 2026-04-01 | In-Progress |  | No impacted claims | 2026-08-26
222 | 2026-07-30 | Podiatric fee schedule effective 4/1/26 | Physicians | HFS Inquiry | HFS has updated Podiatric fee schedule effective 4/1/26 | 2026-04-01 | Complete | 2026-08-26 | No impacted claims | 2026-08-17
195 | 2026-05-07 | SUPR service rates, effective 7/1/2025 | SUPR | HFS Inquiry | HFS has sent an additional update on the SUPR service rates, effective 7/1/2025 | 2025-07-01 | Complete | 2026-07-30 | Complete | 2026-08-05 | 2025-07-01 | 2026-07-16
225 | 2026-08-03 | IDOA Enhanced Rate Providers List – July 1, 2026 | Waiver | HFS Inquiry | HFS updated IDOA Enhanced Rate Providers List – July 1, 2026 | 2026-07-01 | No Configuration Required | 2026-08-04 | No impacted claims | 2026-08-04
177 | 2026-02-27 | APR-DRG and EAPG Hospital Rate Calculators Updates | Hospital | HFS Inquiry | HFS updated the APR-DRG and EAPG Hospital Rate Calculators Updates [Edward Hospital & Gottlieb Memorial Hospital rate updates] | 2026-01-01 | Complete | 2026-07-07 | Complete | 2026-07-31 | 2026-01-01 | 2026-05-29
158 | 2026-01-08 | Home Health Fee Schedule Eff 1/1/2025 | Hospital | HFS Inquiry | HFS updated the Home Health Fee Schedule Eff 1/1/2025 | 2025-01-01 | Complete | 2026-07-06 | Complete | 2026-07-28 | 2025-01-01 | 2026-05-15
196 | 2026-05-08 | Home Health Code incorrectly pricing $0 | Home Health | Global Issue | During the updates for the 1/1/2025 Home Health rates, the pricing starting netting $0 on home health codes in error. |  | Complete | 2026-07-06 | Complete | 2026-07-24 | 2025-01-01 | 2026-05-15
200 | 2026-05-27 | Adaptive Behavior Support (ABS) Services Fee Schedule | Physicians | HFS Inquiry | HFS updated Adaptive Behavior Support (ABS) Services Fee Schedule. |  | Complete | 2026-07-24 | No impacted claims | 2026-07-24
208 | 2026-06-10 | SUPR Code H0020 pricing incorrectly | SUPR | Global Issue | CPT H0020 should price at the SUPR weekly rate of $119.98 per updated fee schedule. Claims are under pricing at $25.87 |  | Complete | 2026-07-24 | No impacted claims | 2026-07-24
199 | 2026-05-22 | XQ48 Firing on CMHC Claims in error | CMHC | Global Issue | Claims billed by CMHC providers are incorrectly hitting denial remark XQ48 on codes payable per the fee schedule. |  | Complete | 2026-07-10 | Complete | 2026-07-22 | 2026-04-27 | 2026-06-25
202 | 2026-06-01 | Remark D22 firing in error | Dentist | Global Issue | Remark code D22 (invalid age for this benefit) is firing on claim with code 41899 in error. Per HFS crosswalk this code is allowed 0-99 years of age. |  | Complete | 2026-07-15 | Complete | 2026-07-16
187 | 2026-04-20 | Practitioner Fee Schedule effective 1/1/2026 | Physicians | HFS Inquiry | HFS updated Practitioner Fee Schedule effective 1/1/2026. | 2026-01-01 | Complete | 2026-07-02 | Complete | 2026-07-15 | 2026-01-01 | 2026-04-30
157 | 2026-01-08 | Safety Net Add-on effective 1/1/2026 | Hospital | HFS Inquiry | HFS sent an additional updates on the Safety Net Add-on Calculations effective 1/1/2026 | 2026-01-01 | Complete | 2026-06-30 | Complete | 2026-07-13 | 2026-01-01 | 2026-04-27
198 | 2026-05-19 | Doula Fee Schedule effective 05/01/2026 | Hospital | HFS Inquiry | HFS updated Doula Fee Schedule effective 05/01/2026 | 2026-05-01 | Complete | 2026-07-08 | No impacted claims | 2026-07-08
206 | 2026-06-09 | DME Fee Schedule Effective 01/01/2026 | Physicians | HFS Inquiry | HFS updated DME Fee Schedule Effective 01/01/2026 | 2026-01-01 | Complete | 2026-07-01 | Complete | 2026-07-07 | 2026-01-01 | 2026-06-23
214 | 2026-07-01 | DHS-DRS rate increase effective 7/1/26 | Physicians | HFS Inquiry | HFS has updated DHS-DRS rate increase effective 7/1/26. | 2026-07-01 | No Configuration Required | 2026-07-01 | No impacted claims | 2026-07-01
119 | 2025-10-09 | Professional Therapy Pricing Incorrect | Therapy | Global Issue | Professinal claims billed with PT/OT/ST are pricing with incorrect unit rates and applying 2.7% reduction twice in error. This is not affecting all therapy claims. |  | Complete | 2026-05-18 | Complete | 2026-06-26 | 2025-11-26 | 2026-04-22
179 | 2026-03-12 | MPA MHVA Final Rates effective 01/01/2026 | Hospital | HFS Inquiry | HFS sent an additional update: Updated MPA MHVA Final Rates effective January 1, 2026. | 2026-01-01 | Complete | 2026-06-25 | No impacted claims | 2026-06-25
186 | 2026-04-20 | APR-DRG and EAPG Hospital Rate Calculators Updates effective 01.01.26. | Hospital | HFS Inquiry | HFS updated APR-DRG and EAPG Hospital Rate Calculators Updates for Graham Hospital’s effective 01.01.26. | 2026-01-01 | No Configuration Required | 2026-06-25 | No impacted claims | 2026-06-25
162 | 2026-01-13 | MPA MHVA Final Rates effective 01/01/2026 | Hospital | HFS Inquiry | HFS sent an additional update: Updated MPA MHVA Final Rates effective January 1, 2026. | 2026-01-01 | Complete | 2026-06-24 | No impacted claims | 2026-06-24
152 | 2025-12-30 | Observation code G0379 pricing in error | Hospital | Global Issue | Observation code G0379 should always price $0 when billed with G0378 per IAMHP guidelines. Line is now pricing additional dollars on claims in error. |  | Complete | 2026-03-24 | Complete | 2026-06-18 | 2025-12-31 | 2026-02-26
201 | 2026-05-27 | Licensed Practitioners of the Healing Arts (LPHA) Fee Schedule Effective 01/01/2025 | Physicians | HFS Inquiry | HFS updated Licensed Practitioners of the Healing Arts (LPHA) Fee Schedule Effective 01/01/2025. | 2025-01-01 | No Configuration Required | 2026-06-12 | No impacted claims | 2026-06-12
168 | 2026-02-03 | APR-DRG and EAPG Hospital Rate Calculators - Effective 01.01.2026 | Hospital | HFS Inquiry | HFS Updated APR-DRG and EAPG Hospital Rate Calculators - Effective 01.01.2026 | 2026-01-01 | Complete | 2026-07-07 | Complete | 2026-06-03 | 2026-01-01 | 2026-02-26
192 | 2026-05-06 | Additional review on remark X218 firing | Physicians | Global Issue | X218 is firing incorrectly on claims for anesthesia add on codes when billed correctly after the primary anesthesia code. |  | Complete | 2026-05-26 | No impacted claims | 2026-05-26
185 | 2026-04-15 | Cell Gene Therapy (CGT) Access Model Effective 1/1/2026 | Hospital | HFS Inquiry | The Cell and Gene Therapy (CGT) Access Model. The administration period of the Model begins January 1, 2026, and continues through December 31, 2030. | 2026-01-01 | Complete | 2026-05-21 | No impacted claims | 2026-05-25
188 | 2026-04-20 | Podiatry Fee Schedule effective 1/1/2026 | Physicians | HFS Inquiry | HFS updated Podiatry Fee Schedule effective 1/1/2026. | 2026-01-01 | Complete | 2026-05-13 | No impacted claims | 2026-05-22
184 | 2026-04-02 | 2025 Air Ambulance Claims Underpaying | Air Ambulance | Global Issue | Air Ambulance claims not paying per the 2025 fee schedule. Underpaying based on prior fee schedules. |  | Complete | 2026-04-27 | Complete | 2026-05-21 | 2025-01-01 | 2025-12-31
190 | 2026-04-27 | Audiology Fee Schedule effective 01/01/2026 | Physicians | HFS Inquiry | HFS updated Audiology Fee Schedule effective 01/01/2026. | 2026-01-01 | Complete | 2026-05-13 | No impacted claims | 2026-05-18
175 | 2026-02-27 | X739 Denying on Co-surgeon claims in error | Physicians | Global Issue | Co Surgeon claims billed with modifier 62 should be excluded from this edit only allowing reimbursement on 1 claim per lifetime. If Co surgeons bill need to allow both claims billed. |  | Complete | 2026-05-11 | Complete | 2026-05-15 | 2024-10-23 | 2026-04-23
189 | 2026-04-21 | Safety net add-on effective 01/01/2026 | Hospital | HFS Inquiry | Hfs updated Safety net add-on effective 01/01/2026 | 2026-01-01 | No Configuration Required | 2026-04-21 | No impacted claims | 2026-04-21
171 | 2026-02-13 | Hand Pricing Logic X304 not pricing claims | DME | Global Issue | X304 firing on claims and not defaulting to any hand pricing methodology |  | Complete | 2026-04-17 | Complete | 2026-04-20 | 2026-04-17 | 2026-04-17
164 | 2026-01-26 | SNF/SMHRF/SLP MCO Rates Effective 1/1/2026 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted updated rates for SNF/County/SMHRF/SLP effective 01/01/2026. This is an additional update from prior version received. | 2026-01-01 | Complete | 2026-03-04 | Complete | 2026-04-08 | 2026-01-01 | 2026-02-12
160 | 2026-01-14 | Practitioner Fee Schedule Effective 10/1/2025 | Physicians | HFS Inquiry | HFS updated the Practitioner Fee Schedule effective 10/1/2025 | 2025-10-01 | Complete | 2026-03-16 | Complete | 2026-04-06 | 2025-10-01 | 2025-12-30
165 | 2026-01-27 | School Based Health Services Fee Schedule Effective 10/1/2025 | Physicians | HFS Inquiry | HFS updated the School Based Health Services Fee Schedule Effective 10/1/2025. | 2025-10-01 | Complete | 2026-04-06 | No impacted claims | 2026-04-06
93 | 2025-08-14 | XQ84 Denial firing incorrectly on ABS Services | BHC | Global Issue | XQ84 denying incorrectly on ABS services when billed from a Behavioral Health Clinic. |  | Complete | 2026-04-02 | Complete | 2026-04-02
155 | 2025-11-24 | Implementation of New Claim Edits for Attending Provider | SNF/LTC/SMHRF/SLF | HFS Inquiry | The Attending Provider NPI field is required for all long term care (LTC) claims. Effective with dates of service on and after January 1, 2026, the Department will reject claims if the Attending Provider is not enrolled with the Department on the date of service. | 2026-01-01 | No Configuration Required | 2026-02-27 | Complete | 2026-04-01
145 | 2025-12-12 | Home Visiting Organization Enrollment and Billing Effective 11.21.2025 | Physicians | HFS Inquiry | Medicaid Coverage for Home Visiting Services – Provider Enrollment and Billing Guidance (Effective November 21, 2025) | 2025-11-21 | Complete | 2026-03-20 | No impacted claims | 2026-03-20
178 | 2026-03-12 | Nursing Facility Per Diem Rate Notices - Stearns Nursing and Rehab 7/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS has updated the Nursing Facility Per Diem Rate Notices - Stearns Nursing and Rehab effective 7/1/2025. | 2025-10-01 | Complete | 2026-03-20 | No impacted claims | 2026-03-20
134 | 2025-11-04 | Waiver Rate Updates Effective 1/1/2026 | Waiver | HFS Inquiry | HFS submitted rate updates 3 DRS waiver services effective 1/1/2026 | 2026-01-01 | Complete | 2026-03-04 | Complete | 2026-03-12 | 2026-01-01 | 2026-02-11
163 | 2026-01-27 | Practitioner Fee Schedule Effective 12/31/2025 | Physicians | HFS Inquiry | HFS updated the Practitioner Fee Schedule effective 12/31/2025. | 2025-12-31 | Complete | 2026-03-09 | No impacted claims | 2026-03-09
167 | 2026-01-30 | Observation claims denying XP18 in error | Hospital | Global Issue | Observation claims are denying the full claim with XP18 in error. |  | Complete | 2026-02-23 | No impacted claims | 2026-02-23
151 | 2025-12-22 | MPA and MHVA Rates – Effective 01/01/2026 | Hospital | HFS Inquiry | The final 2026 MPA (Medicaid Perinatal Add-on) and MHVA (Mental Health Value Add) rates, which will be effective from January 1, 2026. | 2026-01-01 | Complete | 2026-02-17 | No impacted claims | 2026-02-17
146 | 2025-12-08 | Updated LTC and SLP Rates Effective 10/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS updated the rates for LTC and SLP facilities effective 10/1/2025 | 2025-12-01 | Complete | 2026-01-08 | Complete | 2026-02-16 | 2025-10-01 | 2025-12-25
161 | 2026-01-13 | Podiatry Fee Schedule Effective 10/1/2025 | Physicians | HFS Inquiry | HFS updated Podiatry Fee Schedule Effective 10/1/2025 | 2025-10-01 | Complete | 2026-02-12 | No impacted claims | 2026-02-12
94 | 2025-08-18 | SNF/County/SMHRF/SLP MCO Rates Effective 7/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted updated rates for SNF/County/SMHRF/SLP effective 07/01/2025. This is an additional update from prior version received. | 2025-07-01 | Complete | 2025-11-07 | Complete | 2026-02-02 | 2025-07-01 | 2025-09-30
117 | 2025-10-08 | SMHRFs Facility Rates Updates Effective 7/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted updated SMHRF rates effective 7/1/2025. Prior notification sent out had incorrect rates included. | 2025-07-01 | Complete | 2025-11-07 | Complete | 2026-02-02 | 2025-07-01 | 2025-09-30
140 | 2025-12-11 | 2026 FQHC Rates | FQHC/ERC/RHC | HFS Inquiry | HFS updated FQHC rate effective 1/1/2026 | 2026-01-01 | Complete | 2026-01-19 | Complete | 2026-01-30 | 2026-01-01 | 2026-01-06
166 | 2026-01-08 | 2026 Rural Health Clinic (RHC) Rates | FQHC/ERC/RHC | HFS Inquiry | HFS updated medical rates for recently attested Rural Health Clinic (RHC) Rates for 2026 calendar year. | 2026-01-01 | Complete | 2026-01-29 | No impacted claims | 2026-01-30
110 | 2025-09-22 | Practitioner Fee Schedule Effective 7/1/2025 | Physicians | HFS Inquiry | HFS updated the Practitioner Fee Schedule effective 7/1/2025 |  | Complete | 2025-10-16 | Complete | 2026-01-29 | 2025-04-01 | 2025-09-25
150 | 2025-12-22 | 2026 Rural Health Clinic (RHC) Rates | FQHC/ERC/RHC | HFS Inquiry | HFS updated medical rates for recently attested Rural Health Clinic (RHC) Rates for 2026 calendar year. | 2025-12-22 | Complete | 2026-01-29 | No impacted claims | 2026-01-29
95 | 2025-08-14 | 2025 Nursing Facility Per Diem Rate Updates | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted updated rates between May and July 2025 to certain LTC Facilities. Updates included appeals, capital, support, nursing rates, and some quarterly changes. |  | Complete | 2025-11-11 | Complete | 2026-01-23
133 | 2025-08-13 | MAT Code H0020 Netting $0 | SUPR | Global Issue | Corrected claims billed with H0020 for MAT services are not pricing when billed within guidelines. Original denial is XB05 and after corrected are netting $0 with MX remark. Only isolated to providers sbmitted corrected claims for code H0020. |  | Complete | 2026-01-06 | Complete | 2026-01-23
147 | 2025-11-19 | Remark XC35 firing on Diabetes Prevention Program Codes | Physicians | Global Issue | XC35 remark is incorrectly firing on claims billed as telehealth. Telehealth billing is allowed for these services. |  | Complete | 2026-01-16 | Complete | 2026-01-23
135 | 2025-11-18 | Renal Dialysis Add-on Payment Update Effective 1/1/2025 | Dialysis | HFS Inquiry | HFS updated guidance on the renal dialysis add ons effective 1/1/2025. Expanding coverage to additional dialysis revenue codes. |  | Complete | 2025-11-27 | Complete | 2026-01-20 | 2025-01-01 | 2025-11-25
148 | 2025-11-19 | X998 Firing Incorrectly on Diabetes Prevention Program Codes | Physicians | Global Issue | X998 is firing incorrectly when billed correctly with billing taxonomy |  | Complete | 2026-01-16 | Complete | 2026-01-20
149 | 2025-12-19 | Air Ambulance Paying Incorrectly | Air Ambulance | Global Issue | Air ambulance claims incorrectly pricing for service dates in 2025 |  | Complete | 2026-01-16 | Complete | 2026-01-20 | 2024-07-12 | 2026-01-12
112 | 2025-09-26 | Nursing Facility Per Diem Rate Update Effective 7/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted updates to the facilities nursing rate utilization add-ons and staffing add-ons effective 7/1/2025. |  | Complete | 2025-12-04 | Complete | 2026-01-16 | 2025-07-01 | 2025-11-21
156 | 2026-01-08 | Nursing Facility Per Diem Rate Update Effective 7/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS updated the Nursing Facility Per Diem Rate Update for Evercare of Edwardsville Nursing Facility Per Diem Rate Update Effective 7/1/2025 | 2025-07-01 | No Configuration Required | 2026-01-16 | No impacted claims | 2026-01-16
159 | 2026-01-08 | Outpatient High Volume Hospital Determination efective 1/1/2026 | Hospital | HFS Inquiry | HFS updated Outpatient High Volume Hospital Determination effective 1/1/2026. | 2026-01-01 | No Configuration Required | 2026-01-08 | No impacted claims | 2026-01-08
87 | 2025-07-25 | XG01 firing on add on codes | Physicians | Global Issue | XG01 remark is firing on claims billed with add on codes. Remark descriptions states another E&M code was billed on the same date and requires modifier 25. Due it being an add on code, the 25 modifier should not be required for both codes to pay. |  | Complete | 2025-12-17 | Complete | 2026-01-06
136 | 2025-11-18 | Hospice Annual Rate Changes Effective 10/1/2025 | Hospital | HFS Inquiry | HFS updated Hospice rates effective October 1, 2025, through September 30, 2026. | 2025-10-01 | Complete | 2025-12-22 | Complete | 2025-12-30
126 | 2025-10-31 | MORP& RPNE Incorrectly firing on professional claims | Physicians | Global Issue | Professional claims incorreclty denying MORP & RPNE for services not requiring an ordering/referring provider. Reprocessing in progress |  | No Configuration Required | 2025-10-31 | Complete | 2025-12-12
38 | 2025-05-05 | Claims denying X165 | Physicians | Global Issue | Claims are denying X165 for incorrect primary DX code being used. Additional review in progress on ensuring edit is editing appropriatly from what was billed. |  | Complete | 2025-11-21 | Complete | 2025-12-03 | 2024-05-19 | 2025-11-19
63 | 2025-06-11 | Macneal Hospital- Rate update | Hospital | HFS Inquiry | HFS confirmed Macneal Hospital should receive rehab rate for COS 029 effective 4/1/2025 | 2025-04-01 | Complete | 2025-10-24 | Complete | 2025-12-02 | 2025-04-01 | 2025-07-31
92 | 2025-08-12 | SLP Rates Effective 4/1/25 underpaying | SNF/LTC/SMHRF/SLF | Global Issue | Two rate sheets received from HFS for 4/1/25 SLP rates. The incorrect one was loaded. In progress to upload the correct rates for SLP providers and reprocess claims. |  | Complete | 2025-10-17 | Complete | 2025-12-02 | 2025-08-14 | 2025-09-18
41 | 2025-04-29 | Practitioner Fee Schedule Updates Effective 1/1/2025 | Physicians | HFS Inquiry | Received HFS notice with updated practitioner fee schedule effective 1/1/2025 | 2025-01-01 | Complete | 2025-07-08 | Complete | 2025-12-01 | 2025-01-01 | 2025-06-13
107 | 2025-09-22 | COVID-19 Fee Schedule Update Effective 7/1/2025 | Physicians | HFS Inquiry | HFS updated the COVID-19 fee schedule effective 7/1/2025. Codes updated 91304, 91320, 91323. Removal of codes 0240U & 0241U. |  | Complete | 2025-11-21 | Complete | 2025-11-28 | 2025-08-27 | 2025-10-28
108 | 2025-09-22 | CCBHC Rate Updates Effective 10/1/2025 | CCBHC | HFS Inquiry | HFS submitted udpated rates for CCBHC Clinics Effective 10/1/2025. |  | Complete | 2025-11-12 | Complete | 2025-11-28 | 2025-10-01 | 2025-10-27
114 | 2025-10-03 | XP64 Early Delivery Denial In Error | Hospital | Global Issue | XP64 dening incorrectly on diagnosis code O99.52. This diagnosis code is eligible for early deliveries. Reviewing list of all early delivery diagnosis codes to ensure they align with notices. |  | Complete | 2025-11-26 | Complete | 2025-11-28 | 2024-05-10 | 2025-11-26
73 | 2025-06-26 | 2025 DME Fee Schedule | DME | HFS Inquiry | HFS udpated DME Fee Schedule Update Effective 1/1/2025 | 2025-01-01 | Complete | 2025-10-23 | Complete | 2025-11-27 | 2025-01-01 | 2025-06-01
91 | 2025-08-01 | SIA (service intensity add on) not pricing on hospice claims | Hospice | Global Issue | Service intensity add on payments for rev codes 055X and 056X are not pricing on claims when billed correctly per hospice guidelines |  | Complete | 2025-11-14 | Complete | 2025-11-25 | 2025-03-24 | 2025-09-25
109 | 2025-09-22 | Doula fee schedule Updated 9/22/2025 | Doula | HFS Inquiry | HFS updated the Doula Fee Schedule Effective 9/22/2025 |  | Complete | 2025-11-21 | Complete | 2025-11-24 | 2024-01-01 | 2025-11-04
101 | 2025-09-04 | Claims Denying with Remark X161 | Physicians | Global Issue | Claims are denying with remark X161 (The DX code is invalid or disabled). Updates in progress for those claims incorrectly receiving remark. Isolated to hospice and long term care claims. |  | Complete | 2025-11-14 | Complete | 2025-11-21 | 2025-09-02 | 2025-09-09
116 | 2025-10-08 | DME Fee Schedule Codes Updated 4/1/25 per HFS Key | DME | Global Issue | 3 codes were called out on the DME Fee Schedule key with changes effective 4/1/25 and not 1/1/25. Codes L8010, A4453, & A4459 need reviewed to determine correct effective date of changes were updated within the system. |  | Complete | 2025-11-19 | Complete | 2025-11-19 | 2025-01-01 | 2025-03-31
103 | 2025-09-09 | Podiatrist Fee Schedule Effective 4/1/2025 | Physicians | HFS Inquiry | HFS updated Podiatry Fee Schedule Effective 4/1/25 | 2025-04-01 | Complete | 2025-10-01 | Complete | 2025-11-17 | 2025-04-01 | 2025-08-29
120 | 2025-10-09 | Doulas Claims not pricing | Doula | Global Issue | Doula claims not pricing when billed correctly and provider registration aligns. These claims netting $0 with an MX remark code in error. |  | Complete | 2025-11-17 | No impacted claims | 2025-11-17
124 | 2025-10-27 | SNF/County/SMHRF/SLP MCO Rates Effective 10/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS updated LTC rates effective 10/1/25. Per HFS, updated rates forthcoming | 2025-10-01 | No Configuration Required | 2025-11-07 | No impacted claims | 2025-11-07
78 | 2025-07-01 | Updated APR-DRG and EAPG Hospital Rate Calculators Effective 4/1/2025 | Hospital | HFS Inquiry | HFS updated the most recent APR-DRG and EAPG rates effective 4/1/2025. | 2025-04-01 | Complete | 2025-10-17 | Complete | 2025-11-05 | 2025-04-01 | 2025-07-31
111 | 2025-09-26 | Podiatry Fee Schedule Update Effective 9/1/2025 | Podiatrist | HFS Inquiry | HFS submitted updates to the Podiatry Fee Schedule effective 9/1/2025. Updates only pertain to codes 11981 & 11982. |  | Complete | 2025-11-04 | No impacted claims | 2025-11-04
52 | 2025-05-21 | Preventive Visit and Female Annual Exam Visit within a year allowed | Physicians | Global Issue | 1PYM Firing in error on preventive female visit billed within the same year as a regular preventive visit. Practitioner handbook allows both within the same benefit period. |  | Complete | 2025-09-01 | Complete | 2025-10-30 | 2024-06-02 | 2025-08-06
122 | 2025-10-14 | Pend WNC denials for review | Waiver | Global Issue | Moving WNC denial to a pend queue for manual review. To mitigate abrasion we are requesting that Waiver claims be pended to a queue and a manual review occur to confirm if the member has an active service plan on the date of service |  | Complete | 2025-10-20 | No impacted claims | 2025-10-20
104 | 2025-09-09 | School Based Health Services Fee Schedule | Physicians | HFS Inquiry |  | 2025-04-01 | Complete | 2025-10-17 | No impacted claims | 2025-10-17
102 | 2025-09-04 | XA16 (CBS CANNOT BE DETERMINED FOR THIS CLAIM) firing on incorrect hospice rev code 658 | Hospice | Global Issue | XA16 is incorrectly denying on hospice rev code 0658. This revenue code does not apply CBSA Wage Component pricing. |  | Complete | 2025-10-10 | Complete | 2025-10-14
64 | 2025-06-06 | X3 Denial on Valid Codes | Hospital | Global Issue | Edit is currently denying claims with remark X3 for valid principal procedure codes billed. |  | Complete | 2025-09-01 | Complete | 2025-10-08
125 | 2025-10-31 | MORP Denying Incorrectly for Waiver Services | Waiver | Global Issue | MORP incorrectly denying on waiver codes. Ordering and referring providers not required on these services. Updates in progress along with reprocessing. |  |  | 2025-09-25 | Complete | 2025-09-29
79 | 2025-06-30 | X403 Denial Review | Hospital | Global Issue | Claims are denyin X403 for ER services. Remark description: Claim does not contain the appropriate ER, observation or psychiatric clinic services for Illinois Medicaid. These are APL claim requirements that are no longer required. |  | Complete | 2025-09-19 | Complete | 2025-09-22
83 | 2025-07-18 | Nursing Facility Per Diem Rate Notices | SNF/LTC/SMHRF/SLF | HFS Inquiry | Attached are two Rate sheets, with the first attachment having several facilities within. All are changes due to appeals. 1) BLTC-BRDA PDF RATE SHEETS - NOT QTRLY (retro, capital, other) · 6012827 AVANTARA OF ELGIN · 6012553 BELLA TERRA SCHAUMBURG · 6014195 WARREN BARR BUFFALO GROVE · CITADEL OF GLENVIEW, THE | 2025-04-01 | Complete | 2025-08-22 | Complete | 2025-09-19
89 | 2025-07-31 | Remove Oxygen from MLTSS Benefit Coverage | DME | Global Issue | Oxygen code E1390 is not covered by the state for MLTSS members. Update to configuration needed to ensure it denies if billed. |  | Complete | 2025-08-13 | Complete | 2025-09-12 | 2024-08-12 | 2025-08-12
86 | 2025-07-25 | Professional Psych claim paying over billed charges | Physicians | Global Issue | Psych Professional Claims paying over billed amount in error and not capping at billed charges. |  | Complete | 2025-09-08 | No impacted claims | 2025-09-08
90 | 2025-08-01 | T1505 Denying MLTSS in error | Waiver | Global Issue | T1505 is denying MLTS in error when waiver code is within benefit. |  | Complete | 2025-08-14 | Complete | 2025-09-03 | 2024-02-13 | 2025-08-13
82 | 2025-07-18 | Outpatient Therapy Codes applying hand pricing methdology in error | Therapy | Global Issue | Outpatient home health therapy codes are applying hand pricing methodology in error instead of fee schedule pricing. |  | Complete | 2025-08-07 | Complete | 2025-08-29 | 2025-06-13 | 2025-07-21
99 | 2025-08-20 | Remove the PLH hold for Planned Parenthood 362170901 |  | HFS Inquiry | Per guidance received from HFS today please remove the PLH hold from TIN 362170901 Per HFS we can resume claims payment for all dates of service effective immediately. |  | Complete | 2025-08-29 | No impacted claims | 2025-08-29
42 | 2025-05-16 | CMHC Codes denying for MLTSS Members | CMHC | Global Issue | Claims are denying MLTS for CMHC Codes for MLTSS members in error. Providers registered for COS 047 & 34 are eligible to bill for MLTSS services. |  | Complete | 2025-08-04 | Complete | 2025-08-20 | 2024-01-25 | 2025-07-25
98 | 2025-08-14 | ALTON MEMORIAL HOSPITAL | Hospital | HFS Inquiry | Although the latest hospital calculators contain the correct rate information, attached is the corresponding correct rate sheet for Alton Memorial Hospital. |  | No Configuration Required | 2025-08-19 | No impacted claims | 2025-08-19
31 | 2025-04-24 | Code 90837 paying in error when billed by CMHC | CMHC | Global Issue | Procedure code 90837 identified as incorrectly paying when billed by a CMHC provider. Code not payable per CMHC billing fee schedule. |  | Complete | 2025-07-25 | Complete | 2025-08-14
62 | 2025-06-09 | Montrose Hospitals MHVA/MPA | Hospital | HFS Inquiry | HFS sent incorrect add ons for Adult and Childrens facility. Per confirmation from HFS in this ticket, we have recieved the correct add on rates for MPA/MHVA. Recalc will be requried to adjust under and overpayments. | 2025-01-01 | Complete | 2025-07-31 | Complete | 2025-08-07 | 2025-01-01 | 2025-07-16
68 | 2025-06-23 | Incorrect S2 Therapy Denials | Therapy | Global Issue | Requesting report for all S2 denials on therapy codes with date of service 3/1/25 to current. Claims incorrectly denied with authorization will be reprocessed. |  | No Configuration Required |  | Complete | 2025-08-06
53 | 2025-05-27 | Licensed Practitioner of the Healing Arts Fee schedule | Physicians | HFS Inquiry | HFS updated LPHA Fee Schedule Effective 01/01/2025 | 2025-01-01 | Complete | 2025-06-13 | Complete | 2025-07-28 | 2025-01-01 | 2025-05-21
54 | 2025-05-14 | SNF/SMHRF/SLP MCO Rates | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS updated SNF, SMHRF and SLP rates effective 04/01/2025. | 2025-04-01 | Complete | 2025-06-18 | Complete | 2025-07-23 | 2025-04-01 | 2025-06-04
44 | 2025-05-14 | Renal Dialysis Add-on Payment | Dialysis | HFS Inquiry | HFS updated new $95 Dialysis Add on payment for free standing dialysis centers treating members in LTC facility for home dialyis rev codes 841 & 851 | 2025-05-01 | Complete | 2025-06-24 | Complete | 2025-07-22
59 | 2025-06-03 | Additional Practitioner fee schedule update Effective 1/1/2025 | Physicians | HFS Inquiry | HFS made additional update to the practitioner fee schedule effective 1/1/25 with missing codes 87564, 87594, & 876265 | 2025-01-01 | Complete | 2025-06-18 | Complete | 2025-07-22 | 2025-01-01 | 2025-06-06
81 | 2025-07-15 | XQ07 Firing on ABS Services | Physicians | Global Issue | Claims incorrectly denying XQ07 when billed correctly for ABS services. |  | No Configuration Required | 2025-07-15 | Complete | 2025-07-15
11 | 2024-11-06 | Psych Add Ons not applying on Physician claims | Physicians | Global Issue | Psych add ons are incorrectly not applying to physicians who are registered with psychiatric specialty on IMPACT file. |  | Complete | 2025-06-02 | Complete | 2025-07-11
35 | 2025-04-29 | Waiver Code T1505 not assigned rate | Waiver | Global Issue | Claims billed with waiver code T1505 are not pricing per waiver fee schedule. |  | Complete | 2025-06-09 | Complete | 2025-07-11 | 2023-11-27 | 2025-05-27
48 | 2025-05-19 | Optometric Fee Schedule | Physicians | HFS Inquiry | HFS udpated Optometric Fee Schedule Effective 01/01/2025 | 2025-01-01 | Complete | 2025-06-03 | Complete | 2025-07-04 | 2025-01-01 | 2025-05-22
58 | 2025-06-03 | DRS waivers updates 7/1/25 Rate | Waiver | HFS Inquiry | CMS approval received for waiver rate updates effective 7/1/25 | 2025-07-01 | Complete | 2025-06-26 | No impacted claims | 2025-06-26
30 | 2025-04-28 | FQHC Claims Paying with no detail codes | FQHC/ERC/RHC | Global Issue | FQHC claims require detail code to be payable. Claims received with no detail code were allowing payment incorrectly. |  | Complete | 2025-06-13 | Complete | 2025-06-25 | 2024-05-13 | 2025-05-13
2 | 2025-03-27 | Therapy & Evaluation not pricing on the same date Effective 12/1/2024 | Hospital | Global Issue | Per HFS, therap and evaluations are both reimburseable on the same date as of 12/1/24. Configuration not setup correctly to price both services. |  | Complete | 2025-05-16 | Complete | 2025-06-23 | 2024-12-01 | 2025-04-21
14 | 2025-04-03 | SMHRF Reimbursement Changes | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS sent clarification on the SMHRF all inclusive per diem rate and which facilities it applies to | 2025-01-01 | Complete | 2025-05-12 | Complete | 2025-06-18 | 2025-01-01 | 2025-04-22
55 | 2025-05-29 | MMR Vaccination for Children | Physicians | HFS Inquiry | HFS posted notice for MMR Vaccination for Children Aged 6 through 11 Months effective May 5, 2025 | 2025-05-05 | Complete |  | Complete | 2025-06-17
10 | 2025-01-28 | Outpatient Dialysis paying incorrectly | Dialysis | Global Issue | Outpatient dialysis per diem pricing not applying to all dialysis revenue codes. Pricing defaulting to EAPG incorrectly. |  | Complete | 2025-06-05 | Complete | 2025-06-10
1 | 2025-03-28 | Code J8499 not hand pricing correctly | Physicians | Global Issue | Procedure code J8499 was not pricing per hand methodology correctly |  | Complete | 2025-06-06 | No impacted claims | 2025-06-06
13 | 2025-04-01 | Nursing Facility Per Diem Rate Notices - Capital Rate | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted capital rate updates for nursing facilities effective 1/1/2025 | 2025-01-01 | Complete | 2025-05-07 | Complete | 2025-06-06 | 2025-01-01 | 2025-04-25
21 | 2025-01-29 | Revised APR-DRG and EAPG Hospital Rate Calculators | Hospital | HFS Inquiry | Inpatient/Outpatient Hospital Rate Updates Effective 1/1/2025 | 2025-01-01 | Complete | 2025-04-15 | Complete | 2025-06-04 | 2025-01-01
8 | 2025-02-28 | Remove 6 Visit Claims Counting Rule for PT/OT ST | Physicians | Global Issue | Effective 3/1/25 all therapy visits require prior authorization for PT/OT/ST services. |  | Complete | 2025-05-06 | No impacted claims | 2025-05-06
191 | 2026-04-27 | Nursing Facility Per Diem Rate Correction – Aliya of Glenwood Rate Sheets (Notice of Correction) Effective 04/01/2026 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS corrected the Nursing Facility Per Diem Rate Correction – Aliya of Glenwood Rate Sheets (Notice of Correction) Effective 04/01/2026. | 2026-04-01 | Complete | 2026-05-27 | No impacted claims
193 | 2026-05-07 | School Based/Linked Health Center Fee Schedule effective 1/1/2026 | Physicians | HFS Inquiry | HFS updated School Based/Linked Health Center Fee Schedule effective 1/1/2026 | 2026-01-01 | Complete | 2026-05-11 | No impacted claims
194 | 2026-05-07 | Nursing Facility Per Diem Rate Notices - Arc at Kankakee Rate Sheets Effective 04/01/2026. | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS has sent an additional update on the Nursing Facility Per Diem Rate Notices for provider Arc at Kankakee Rate Sheets [new] Effective 04/01/2026. | 2026-04-01 | Complete | 2026-06-04 | No impacted claims