## Open
ID | Open Date | Project | Provider Type | Inquiry Type | Description | Effective Date | Configuration Status | Config Ticket Completion Date | Claims Status | Claims Ticket Completion Date | Impacted Claim Start Date | Impacted Claim End Date
24 | 2024-10-22 | Hospice Annual Rate Changes | Hospice | HFS Inquiry | HFS submitted hospice rate updates effective 10/1/2024. All rates have been loaded. Pricing issue being tracked seperatly. | 2024-10-01 | In-Progress |  | Waiting for Configuration
67 | 2024-10-23 | Hospice Underpayments | Hospice | Global Issue | Hospice claims are under review that are pricing revenue code 0651 incorrectly. This is only affecting this revenue code and not all hospice claims. |  | In-Progress |  | Waiting for Configuration
41 | 2025-04-29 | Practitioner Fee Schedule Updates Effective 1/1/2025 | Physicians | HFS Inquiry | Received HFS notice with updated practitioner fee schedule effective 1/1/2025 | 2025-01-01 | Complete | 2025-07-08 | In Progress |  | 2025-01-01 | 2025-06-13
63 | 2025-06-11 | Macneal Hospital- Rate update | Hospital | HFS Inquiry | HFS confirmed Macneal Hospital should receive rehab rate for COS 029 effective 4/1/2025 | 2025-04-01 | Complete | 2025-10-24 | In Progress |  | 2025-04-01 | 2025-07-31
73 | 2025-06-26 | 2025 DME Fee Schedule | DME | HFS Inquiry | HFS udpated DME Fee Schedule Update Effective 1/1/2025 | 2025-01-01 | Complete | 2025-10-23 | In Progress |  | 2025-01-01 | 2025-06-01
78 | 2025-07-01 | Updated APR-DRG and EAPG Hospital Rate Calculators Effective 4/1/2025 | Hospital | HFS Inquiry | HFS updated the most recent APR-DRG and EAPG rates effective 4/1/2025. | 2025-04-01 | Complete | 2025-10-17 | In Progress |  | 2025-04-01 | 2025-07-31
87 | 2025-07-25 | XG01 firing on add on codes | Physicians | Global Issue | XG01 remark is firing on claims billed with add on codes. Remark descriptions states another E&M code was billed on the same date and requires modifier 25. Due it being an add on code, the 25 modifier should not be required for both codes to pay. |  | In-Progress |  | Waiting for Configuration
91 | 2025-08-01 | SIA (service intensity add on) not pricing on hospice claims | Hospice | Global Issue | Service intensity add on payments for rev codes 055X and 056X are not pricing on claims when billed correctly per hospice guidelines |  | Complete | 2025-11-14 | In Progress
92 | 2025-08-12 | SLP Rates Effective 4/1/25 underpaying | SNF/LTC/SMHRF/SLF | Global Issue | Two rate sheets received from HFS for 4/1/25 SLP rates. The incorrect one was loaded. In progress to upload the correct rates for SLP providers and reprocess claims. |  | Complete | 2025-10-17 | In Progress |  | 2025-08-14 | 2025-09-18
133 | 2025-08-13 | MAT Code H0020 Netting $0 | SUPR | Global Issue | Corrected claims billed with H0020 for MAT services are not pricing when billed within guidelines. Original denial is XB05 and after corrected are netting $0 with MX remark. Only isolated to providers sbmitted corrected claims for code H0020. |  | In-Progress |  | Waiting for Configuration
93 | 2025-08-14 | XQ84 Denial firing incorrectly on ABS Services | BHC | Global Issue | XQ84 denying incorrectly on ABS services when billed from a Behavioral Health Clinic. |  | In-Progress |  | Waiting for Configuration
95 | 2025-08-14 | 2025 Nursing Facility Per Diem Rate Updates | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted updated rates between May and July 2025 to certain LTC Facilities. Updates included appeals, capital, support, nursing rates, and some quarterly changes. |  | Complete | 2025-11-11 | In Progress
97 | 2025-08-14 | 2025 Rural Health Clinic (RHC) Rates | FQHC/ERC/RHC | HFS Inquiry | HFS updated medical rates for recently attested Rural Health Clinic (RHC) Rates for 2025 calendar year. |  | In-Progress |  | Waiting for Configuration
94 | 2025-08-18 | SNF/County/SMHRF/SLP MCO Rates Effective 7/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted updated rates for SNF/County/SMHRF/SLP effective 07/01/2025. This is an additional update from prior version received. |  | Complete | 2025-11-07 | In Progress |  | 2025-07-01 | 2025-09-30
107 | 2025-09-22 | COVID-19 Fee Schedule Update Effective 7/1/2025 | Physicians | HFS Inquiry | HFS updated the COVID-19 fee schedule effective 7/1/2025. Codes updated 91304, 91320, 91323. Removal of codes 0240U & 0241U. |  | In-Progress |  | Waiting for Configuration
108 | 2025-09-22 | CCBHC Rate Updates Effective 10/1/2025 | CCBHC | HFS Inquiry | HFS submitted udpated rates for CCBHC Clinics Effective 10/1/2025. |  | Complete | 2025-11-12 | In Progress |  | 2025-10-01 | 2025-10-27
110 | 2025-09-22 | Practitioner Fee Schedule Effective 7/1/2025 | Physicians | HFS Inquiry | HFS updated the Practitioner Fee Schedule effective 7/1/2025 |  | Complete | 2025-10-16 | In Progress |  | 2025-04-01 | 2025-09-25
112 | 2025-09-26 | Nursing Facility Per Diem Rate Update Effective 7/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted updates to the facilities nursing rate utilization add-ons and staffing add-ons effective 7/1/2025. |  | In-Progress |  | Waiting for Configuration
114 | 2025-10-03 | XP64 Early Delivery Denial In Error | Hospital | Global Issue | XP64 dening incorrectly on diagnosis code O99.52. This diagnosis code is eligible for early deliveries. Reviewing list of all early delivery diagnosis codes to ensure they align with notices. |  | In-Progress |  | Waiting for Configuration
117 | 2025-10-08 | SMHRFs Facility Rates Updates Effective 7/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted updated SMHRF rates effective 7/1/2025. Prior notification sent out had incorrect rates included. |  | Complete | 2025-11-07 | In Progress |  | 2025-07-01 | 2025-09-30
119 | 2025-10-09 | Professional Therapy Pricing Incorrect | Therapy | Global Issue | Professinal claims billed with PT/OT/ST are pricing with different rates. Pricing in review. Not affecting all therapy claims. |  | In-Progress |  | Waiting for Configuration
125 | 2025-10-31 | MORP Denying Incorrectly for Waiver Services | Waiver | Global Issue | MORP incorrectly denying on waiver codes. Ordering and referring providers not required on these services. Updates in progress along with reprocessing. |  | No Configuration Required |  | In Progress
126 | 2025-10-31 | MORP& RPNE Incorrectly firing on professional claims | Physicians | Global Issue | Professional claims incorreclty denying MORP & RPNE for services not requiring an ordering/referring provider. Reprocessing in progress |  | In-Progress |  | Waiting for Configuration
134 | 2025-11-04 | Waiver Rate Updates Effective 1/1/2026 | Waiver | HFS Inquiry | HFS submitted rate updates 3 DRS waiver services effective 1/1/2026 | 2026-01-01 | In-Progress |  | Waiting for Configuration
135 | 2025-11-18 | Renal Dialysis Add-on Payment Update Effective 1/1/2025 | Dialysis | HFS Inquiry | HFS updated guidance on the renal dialysis add ons effective 1/1/2025. Expanding coverage to additional dialysis revenue codes. |  | New |  | Waiting for Configuration
136 | 2025-11-18 | Hospice Annual Rate Changes Effective 10/1/2025 | Hospital | HFS Inquiry | HFS updated Hospice rates effective October 1, 2025, through September 30, 2026. | 2025-10-01 | In-Progress |  | Waiting for Configuration

## Closed
ID | Open Date | Project | Provider Type | Inquiry Type | Description | Effective Date | Configuration Status | Config Ticket Completion Date | Claims Status | Claims Ticket Completion Date | Impacted Claim Start Date | Impacted Claim End Date
11 | 2024-11-06 | Psych Add Ons not applying on Physician claims | Physicians | Global Issue | Psych add ons are incorrectly not applying to physicians who are registered with psychiatric specialty on IMPACT file. |  | Complete | 2025-06-02 | Complete | 2025-07-11 | 2024-01-01 | 2025-11-04
10 | 2025-01-28 | Outpatient Dialysis paying incorrectly | Dialysis | Global Issue | Outpatient dialysis per diem pricing not applying to all dialysis revenue codes. Pricing defaulting to EAPG incorrectly. |  | Complete | 2025-06-05 | Complete | 2025-06-10 | 2025-09-02 | 2025-09-09
21 | 2025-01-29 | Revised APR-DRG and EAPG Hospital Rate Calculators | Hospital | HFS Inquiry | Inpatient/Outpatient Hospital Rate Updates Effective 1/1/2025 | 2025-01-01 | Complete | 2025-04-15 | Complete | 2025-06-04 | 2025-01-01 | 2025-03-31
8 | 2025-02-28 | Remove 6 Visit Claims Counting Rule for PT/OT ST | Physicians | Global Issue | Effective 3/1/25 all therapy visits require prior authorization for PT/OT/ST services. |  | Complete | 2025-05-06 | No impacted claims | 2025-05-06 | 2025-04-01 | 2025-08-29
2 | 2025-03-27 | Therapy & Evaluation not pricing on the same date Effective 12/1/2024 | Hospital | Global Issue | Per HFS, therap and evaluations are both reimburseable on the same date as of 12/1/24. Configuration not setup correctly to price both services. |  | Complete | 2025-05-16 | Complete | 2025-06-23
1 | 2025-03-28 | Code J8499 not hand pricing correctly | Physicians | Global Issue | Procedure code J8499 was not pricing per hand methodology correctly |  | Complete | 2025-06-06 | No impacted claims | 2025-06-06
13 | 2025-04-01 | Nursing Facility Per Diem Rate Notices - Capital Rate | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS submitted capital rate updates for nursing facilities effective 1/1/2025 | 2025-01-01 | Complete | 2025-05-07 | Complete | 2025-06-06
14 | 2025-04-03 | SMHRF Reimbursement Changes | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS sent clarification on the SMHRF all inclusive per diem rate and which facilities it applies to | 2025-01-01 | Complete | 2025-05-12 | Complete | 2025-06-18 | 2024-06-02 | 2025-08-06
31 | 2025-04-24 | Code 90837 paying in error when billed by CMHC | CMHC | Global Issue | Procedure code 90837 identified as incorrectly paying when billed by a CMHC provider. Code not payable per CMHC billing fee schedule. |  | Complete | 2025-07-25 | Complete | 2025-08-14
30 | 2025-04-28 | FQHC Claims Paying with no detail codes | FQHC/ERC/RHC | Global Issue | FQHC claims require detail code to be payable. Claims received with no detail code were allowing payment incorrectly. |  | Complete | 2025-06-13 | Complete | 2025-06-25
35 | 2025-04-29 | Waiver Code T1505 not assigned rate | Waiver | Global Issue | Claims billed with waiver code T1505 are not pricing per waiver fee schedule. |  | Complete | 2025-06-09 | Complete | 2025-07-11
38 | 2025-05-05 | Claims denying X165 | Physicians | Global Issue | Claims are denying X165 for incorrect primary DX code being used. Additional review in progress on ensuring edit is editing appropriatly from what was billed. |  | Complete | 2025-11-21 | Complete
54 | 2025-05-14 | SNF/SMHRF/SLP MCO Rates | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS updated SNF, SMHRF and SLP rates effective 04/01/2025. | 2025-04-01 | Complete | 2025-06-18 | Complete | 2025-07-23
44 | 2025-05-14 | Renal Dialysis Add-on Payment | Dialysis | HFS Inquiry | HFS updated new $95 Dialysis Add on payment for free standing dialysis centers treating members in LTC facility for home dialyis rev codes 841 & 851 | 2025-05-01 | Complete | 2025-06-24 | Complete | 2025-07-22
42 | 2025-05-16 | CMHC Codes denying for MLTSS Members | CMHC | Global Issue | Claims are denying MLTS for CMHC Codes for MLTSS members in error. Providers registered for COS 047 & 34 are eligible to bill for MLTSS services. |  | Complete | 2025-08-04 | Complete | 2025-08-20 | 2024-08-12 | 2025-08-12
48 | 2025-05-19 | Optometric Fee Schedule | Physicians | HFS Inquiry | HFS udpated Optometric Fee Schedule Effective 01/01/2025 | 2025-01-01 | Complete | 2025-06-03 | Complete | 2025-07-04
52 | 2025-05-21 | Preventive Visit and Female Annual Exam Visit within a year allowed | Physicians | Global Issue | 1PYM Firing in error on preventive female visit billed within the same year as a regular preventive visit. Practitioner handbook allows both within the same benefit period. |  | Complete | 2025-09-01 | Complete | 2025-10-30 | 2024-02-13 | 2025-08-13
53 | 2025-05-27 | Licensed Practitioner of the Healing Arts Fee schedule | Physicians | HFS Inquiry | HFS updated LPHA Fee Schedule Effective 01/01/2025 | 2025-01-01 | Complete | 2025-06-13 | Complete | 2025-07-28 | 2025-06-13 | 2025-07-21
55 | 2025-05-29 | MMR Vaccination for Children | Physicians | HFS Inquiry | HFS posted notice for MMR Vaccination for Children Aged 6 through 11 Months effective May 5, 2025 | 2025-05-05 | Complete |  | Complete | 2025-06-17 | 2024-01-25 | 2025-07-25
59 | 2025-06-03 | Additional Practitioner fee schedule update Effective 1/1/2025 | Physicians | HFS Inquiry | HFS made additional update to the practitioner fee schedule effective 1/1/25 with missing codes 87564, 87594, & 876265 | 2025-01-01 | Complete | 2025-06-18 | Complete | 2025-07-22
58 | 2025-06-03 | DRS waivers updates 7/1/25 Rate | Waiver | HFS Inquiry | CMS approval received for waiver rate updates effective 7/1/25 | 2025-07-01 | Complete | 2025-06-26 | No impacted claims |  | 2025-01-01 | 2025-07-16
64 | 2025-06-06 | X3 Denial on Valid Codes | Hospital | Global Issue | Edit is currently denying claims with remark X3 for valid principal procedure codes billed. |  | Complete | 2025-09-01 | Complete | 2025-10-08
62 | 2025-06-09 | Montrose Hospitals MHVA/MPA | Hospital | HFS Inquiry | HFS sent incorrect add ons for Adult and Childrens facility. Per confirmation from HFS in this ticket, we have recieved the correct add on rates for MPA/MHVA. Recalc will be requried to adjust under and overpayments. | 2025-01-01 | Complete | 2025-07-31 | Complete | 2025-08-07 | 2025-01-01 | 2025-05-21
68 | 2025-06-23 | Incorrect S2 Therapy Denials | Therapy | Global Issue | Requesting report for all S2 denials on therapy codes with date of service 3/1/25 to current. Claims incorrectly denied with authorization will be reprocessed. |  | No Configuration Required |  | Complete | 2025-08-06 | 2025-04-01 | 2025-06-04
79 | 2025-06-30 | X403 Denial Review | Hospital | Global Issue | Claims are denyin X403 for ER services. Remark description: Claim does not contain the appropriate ER, observation or psychiatric clinic services for Illinois Medicaid. These are APL claim requirements that are no longer required. |  | Complete | 2025-09-19 | Complete | 2025-09-22
81 | 2025-07-15 | XQ07 Firing on ABS Services | Physicians | Global Issue | Claims incorrectly denying XQ07 when billed correctly for ABS services. |  | No Configuration Required | 2025-07-15 | Complete | 2025-07-15 | 2025-01-01 | 2025-06-06
83 | 2025-07-18 | Nursing Facility Per Diem Rate Notices | SNF/LTC/SMHRF/SLF | HFS Inquiry | Attached are two Rate sheets, with the first attachment having several facilities within. All are changes due to appeals. 1) BLTC-BRDA PDF RATE SHEETS - NOT QTRLY (retro, capital, other) · 6012827 AVANTARA OF ELGIN · 6012553 BELLA TERRA SCHAUMBURG · 6014195 WARREN BARR BUFFALO GROVE · CITADEL OF GLENVIEW, THE | 2025-04-01 | Complete | 2025-08-22 | Complete | 2025-09-19
82 | 2025-07-18 | Outpatient Therapy Codes applying hand pricing methdology in error | Therapy | Global Issue | Outpatient home health therapy codes are applying hand pricing methodology in error instead of fee schedule pricing. |  | Complete | 2025-08-07 | Complete | 2025-08-29
86 | 2025-07-25 | Professional Psych claim paying over billed charges | Physicians | Global Issue | Psych Professional Claims paying over billed amount in error and not capping at billed charges. |  | Complete | 2025-09-08 | No impacted claims | 2025-09-08 | 2023-11-27 | 2025-05-27
89 | 2025-07-31 | Remove Oxygen from MLTSS Benefit Coverage | DME | Global Issue | Oxygen code E1390 is not covered by the state for MLTSS members. Update to configuration needed to ensure it denies if billed. |  | Complete | 2025-08-13 | Complete | 2025-09-12 | 2025-01-01 | 2025-05-22
90 | 2025-08-01 | T1505 Denying MLTSS in error | Waiver | Global Issue | T1505 is denying MLTS in error when waiver code is within benefit. |  | Complete | 2025-08-14 | Complete | 2025-09-03 | 2024-05-13 | 2025-05-13
98 | 2025-08-14 | ALTON MEMORIAL HOSPITAL | Hospital | HFS Inquiry | Although the latest hospital calculators contain the correct rate information, attached is the corresponding correct rate sheet for Alton Memorial Hospital. |  | No Configuration Required | 2025-08-19 | Complete |  | 2024-12-01 | 2025-04-21
99 | 2025-08-20 | Remove the PLH hold for Planned Parenthood 362170901 |  | HFS Inquiry | Per guidance received from HFS today please remove the PLH hold from TIN 362170901 Per HFS we can resume claims payment for all dates of service effective immediately. |  | Complete | 2025-08-29 | Complete |  | 2025-01-01 | 2025-04-22
101 | 2025-09-04 | Claims Denying with Remark X161 | Physicians | Global Issue | Claims are denying with remark X161 (The DX code is invalid or disabled). Updates in progress for those claims incorrectly receiving remark. Isolated to hospice and long term care claims. |  | Complete | 2025-11-14 | Complete | 2025-11-21
102 | 2025-09-04 | XA16 (CBS CANNOT BE DETERMINED FOR THIS CLAIM) firing on incorrect hospice rev code 658 | Hospice | Global Issue | XA16 is incorrectly denying on hospice rev code 0658. This revenue code does not apply CBSA Wage Component pricing. |  | Complete | 2025-10-10 | Complete | 2025-10-14
103 | 2025-09-09 | Podiatrist Fee Schedule Effective 4/1/2025 | Physicians | HFS Inquiry | HFS updated Podiatry Fee Schedule Effective 4/1/25 | 2025-04-01 | Complete | 2025-10-01 | Complete | 2025-11-17
104 | 2025-09-09 | School Based Health Services Fee Schedule | Physicians | HFS Inquiry |  | 2025-04-01 | Complete | 2025-10-17 | No impacted claims | 2025-10-17 | 2025-01-01 | 2025-04-25
109 | 2025-09-22 | Doula fee schedule Updated 9/22/2025 | Doula | HFS Inquiry | HFS updated the Doula Fee Schedule Effective 9/22/2025 |  | Complete | 2025-11-21 | Complete | 2025-11-24 | 2025-01-01
111 | 2025-09-26 | Podiatry Fee Schedule Update Effective 9/1/2025 | Podiatrist | HFS Inquiry | HFS submitted updates to the Podiatry Fee Schedule effective 9/1/2025. Updates only pertain to codes 11981 & 11982. |  | Complete | 2025-11-04 | No impacted claims | 2025-11-04
116 | 2025-10-08 | DME Fee Schedule Codes Updated 4/1/25 per HFS Key | DME | Global Issue | 3 codes were called out on the DME Fee Schedule key with changes effective 4/1/25 and not 1/1/25. Codes L8010, A4453, & A4459 need reviewed to determine correct effective date of changes were updated within the system. |  | Complete | 2025-11-19 | Complete | 2025-11-19
120 | 2025-10-09 | Doulas Claims not pricing | Doula | Global Issue | Doula claims not pricing when billed correctly and provider registration aligns. These claims netting $0 with an MX remark code in error. |  | Complete | 2025-11-17 | No impacted claims | 2025-11-17
122 | 2025-10-14 | Pend WNC denials for review | Waiver | Global Issue | Moving WNC denial to a pend queue for manual review. To mitigate abrasion we are requesting that Waiver claims be pended to a queue and a manual review occur to confirm if the member has an active service plan on the date of service |  | Complete | 2025-10-20 | No impacted claims | 2025-10-20
124 | 2025-10-27 | SNF/County/SMHRF/SLP MCO Rates Effective 10/1/2025 | SNF/LTC/SMHRF/SLF | HFS Inquiry | HFS updated LTC rates effective 10/1/25. Per HFS, updated rates forthcoming | 2025-10-01 | No Configuration Required | 2025-11-07 | No impacted claims | 2025-11-07