## WEBSITE-ISSUE-LOG-UPDATE-12.18
CountyCare Claims and Configuration Project Updates Updated 12/19/2024
# | Type | Remark Code (if applicable) | Project | Impacted Providers | Description | Configuration Completion Date | Resolution | Status
316 | Claim Denial Issue |  | RORP Logic Updates | All providers | Updates to ORP logic to ensure requirements are met for both professional and facility claims outlined in IAMHP billing manual |  | Still in progress | In Progress
425 | Claim Pricing Issue |  | Psych add on not applying | Professional Psych | Identified professional claims not applying psyciatric add on | 2024-07-12 | Configuration completed and claims reprocessing in progress | In Progress
434 | RATE UPDATE - Fee Schedule |  | Updated waiver rates | Waiver | CountyCare received notice of updated rates effective 8/1/2024 for respite and home delivered meal rates | 8/5/2024 and 10/29/24 for Respite Codes | Configuration completed and claims reprocessed | Complete
440 | RATE UPDATE - Fee Schedule |  | Updated Practitioner Fee Schedule Effective 4/1/2024 | Professional | CountyCare received notice from HFS with updates to the Practitioner Fee schedule effective 4/1/2024 | 2024-08-15 | Configuration completed and claims reprocessing in progress (large claims reprocessing project) | In Progress
455 | Claim Denial Issue | X998 | X998 Denial on DPP & DSMES Services | Professional | Claims are incorrectly denying X998 for providers appropriatly registered fo rthe Diabetes Prevention Program (DPP) and the Diabetes Self Management and Education (DSMES) | 2024-11-05 | Configuration completed and claims reprocessing in progress | In Progress
456 | Claim Pricing Issue |  | Incorrect rates on PFS vs the Enhanced Rate tab | Professional | Reopened issue as there are missed reprocessing on claims that were paid on the PFS rate instead of the enhanced rate tab. Working to identify scope of claims reprocessing |  | Claims reprocessing in progress | In Progress
462 | Claim Pricing Issue |  | DSH Payments in error | Hospitals | Claims have incorrectly been applying DSH payments. Updated are in progress and overpayments will be recovered for the past 12 months. Per prior notice from 2014, DSH payments are not made directly by the MCOs. | 2024-09-10 | Configuration completed. Claims reprocessing in progress | In Progress
463 | Claim Pricing Issue |  | APR/DRG Rates | Hospitals | County received updated clarification from HFS that APR/DRG rates are to apply per the discharge date. Currently rates are assigned based on the admission date. | 2024-09-26 | Configuration completed. Claims reprocessing in progress | In Progress
459 | RATE UPDATE - Fee Schedule |  | COVID-19 Fee Schedule | Professional | CountyCare received notice from HFS with revised updates to the COVID-19 Fee Schedule | 2024-10-16 | Configuration completed and claims reprocessed | Complete
460 | RATE UPDATE - Fee Schedule |  | Updated Practitioner Fee Schedule Effective 7/1/2024 | Professional | CountyCare received notice from HFS with revised updates to the Practitioner Fee schedule effective 7/1/2024 | 2024-10-14 | Configuration completed and claims reprocessing in progress | In Progress
465 | RATE UPDATE - Fee Schedule |  | Updated CCBHC PPS rates | Behavioral Health | CountyCare received notice from HFS regarding new CCHBC Clinics Effective 10/1/2024 with assigned PPS rates |  | Configuration in progress | In Progress
477 | Claim Pricing Issue |  | Observation Pricing | Hospitals | CountyCare reviewing observation pricing with HFS and 3M. Provider disputing underpayments. | 2024-11-13 | Pricing udpates completed and claims reprocessing in progress | In Progress
466 | RATE UPDATE - Fee Schedule |  | Updated Pathways Rates | Pathways | CountyCare received notice of updated rates effective 8/1/2024 for Updated Pathways to Success Rates | 2024-11-04 | Configuration completed and claims reprocessing in progress | In Progress
478 | Claim rejection Issue |  | Telehealth claims rejecting in error | All professional claims | Error identified in telehealth edit causing correctly billed telehealth claims to be rejected | 2024-11-13 | Front end edit has been fixed. All claims have been resubmited into the system for normal processing | Complete
471 | RATE UPDATE - Fee Schedule |  | Updated Nursing Rates for Effective 10/1/2024 | SNF | CountyCare received notice of updated rates sheets for a few facilities effective 10/1/2024 | 2024-11-12 | Configuration completed. Claims reprocessing in progress | In Progress
472 | RATE UPDATE - Fee Schedule |  | Updated Podiatrist Fee Schedule | Podiatrist | CountyCare received notice from HFS with revised updates to the Podiatrist Fee Schedule effective 10/1/2024 | 2024-10-15 | Configuration completed. No impacted claims for reprocessing | Complete
473 | RATE UPDATE - Fee Schedule |  | Updated Hospice Annual Rate | Hospice | CountyCare received notice of updated rates effective 10/1/2024 for Hospice Annual Rates |  | Configuration in progress | In Progress
474 | RATE UPDATE -New Billing Guidelines |  | Licensed Genetic Counselors - Enrollment and Billing as a New Provider Type | Genetic Counselors | CountyCare received notice of update for Licensed Genetic Counselors - Enrollment and Billing as a New Provider Type effective 4/1/2024 | 2024-11-21 | Configuration completed. No impacted claims for reprocessing | Complete
480 | Claim rejection Issue |  | Incorrect covered/non covered days rejection | Hospitals | CountyCare is reviewing front end edit for covered plus non covered days. Increase in rejections for this edit | 2024-11-25 | Front end edit has been fixed. All claims rejected in error have been resubmitted | Complete
481 | RATE UPDATE - Fee Schedule |  | Updated Nursing Facility Per Diem Rate | SNF | CountyCare received notice of updated rates sheets for a Aliya of Palos Park with multiple effective dates | 2024-11-25 | Configuration completed. Claims reprocessing in progress | In Progress
482 | Claim Pricing Issue |  | Psychiatric Outpatient Add-on Applying Incorrectly | Outpatient Psychiatric Hospitals | Outpatient pscyhiatric claims are not applying the $113 add on correctly per day. Overpayments identified as claims are paying add on per units billed on the claim |  | Configuration in progress | In Progress
483 | RATE UPDATE - Fee Schedule |  | Updates to Hospital Reimbursement Components† | Hospital | CountyCare received notice of updated rates sheets for Hospital Reimbursement Components† |  | Configuration in progress | In Progress
484 | RATE UPDATE - Billing Change |  | Confirmation of Coverage for Continuous Glucose Monitors† | Professional† | CountyCare received notice of updated of Coverage for Continuous Glucose Monitors† |  | Configuration in progress | In Progress
484 | RATE UPDATE - Billing Change |  | Confirmation of Coverage for Remote Ultrasounds | Professional† | CountyCare received notice of Confirmation of Coverage for Remote Ultrasounds |  | Configuration in progress | In Progress
485 | RATE UPDATE - Fee Schedule |  | Updated Based Behavioral Health Fee Schedule and Billing Guidance | CBHC | CountyCare received notice of updated rates sheets for Based Behavioral Health Fee Schedule and Billing Guidance |  | Configuration in progress | In Progress
486 | RATE UPDATE - Fee Schedule |  | Updated Practitioner Fee Schedule | Professional† | CountyCare received notice from HFS with updates to the Practitioner Fee schedule effective 7/1/2024 |  | Configuration in progress | In Progress
487 | RATE UPDATE - Fee Schedule |  | Updated Practitioner Fee Schedule | Professional† | CountyCare received notice from HFS with updates to the Practitioner Fee schedule effective 10/1/2024 |  | Configuration in progress | In Progress
488 | RATE UPDATE - Fee Schedule |  | Updated Physical, Occupational, and Speech Therapies Fee Schedule and Billing Guidance | Therapist | CountyCare received notice from HFS with updates to the Physical, Occupational, and Speech Therapies Fee Schedule and Billing Guidance |  | Configuration in progress | In Progress
489 | RATE UPDATE - Billing Change |  | Update in Age Limit for Diabetes Prevention and Management Programs | Professional† | CountyCare received notice from HFS with updates to the Age Limit for Diabetes Prevention and Management Programs |  | Configuration in progress | In Progress
490 | RATE UPDATE - Fee Schedule |  | Updated Nursing Facility Per Diem Rate | SNF | CountyCare received notice of updates to rates sheets for a few facilities. |  | Configuration in progress | In Progress
491 | RATE UPDATE - Fee Schedule |  | Updated FQHC rates | FQHC | CountyCare received notice from HFS with updates to the FQHC rates |  | Configuration in progress | In Progress
492 | RATE UPDATE - Billing Change |  | Updated Services for Transgender, Ambiguous Gender, and Hermaphrodite Patients | Professional† | CountyCare received notice from HFS with updates to the Modifier KX and Condition Code 45 on Claims for Services for Transgender, Ambiguous Gender, and Hermaphrodite Patients |  | Configuration in progress | In Progress
493 | RATE UPDATE - Fee Schedule |  | School Based Health Services Fee Schedule | SCBHC | CountyCare received notice from HFS with updates to the School Based Health Clinic Fee Schedule effective 10/1/2024 |  | Configuration in progress | In Progress
494 | RATE UPDATE - Fee Schedule |  | Podiatrist Fee Schedule | Podiatrist | CountyCare received notice from HFS with updates to the Podiatrist Fee schedule effective 10/1/2024 |  | Configuration in progress | In Progress
495 | Claim Denial Issue | MNC | MNC denying incorrectly for revenue codes 0780 | Hospitals | Revenue code 0780 is allowed to bill per HFS as notice posted on 3/2/21. Revenue code is currently denying MNC as non covered in error. |  | Configuration in progress | In Progress
496 | RATE UPDATE - Fee Schedule |  | IP/OP Calculators Eff 1/1/2025 | Hospitals | CountyCare received notice from HFS on the first version of IP/OP calculators effective 1/1/2025 |  | Configuration on hold
497 | RATE UPDATE - Fee Schedule |  | Administration Day Rate Increase | Hospitals | CoutyCare received notice from HFS on an increase to administrative per diem daily rate effective 1/1/2024 |  | Configuration in progress | In Progress
498 | Claim Pricing Issue |  | Podiatrist claims pricing at $0 | Podiatrists | CountyCare reviewing claims for Podiatrists not pricing per the fee schedule rates |  | Configuration in progress